## REKAP (Final Harga Kontrak)
REKAPITULASI RENCANA ANGGARAN BIAYA
PEKERJAAN |  | : | RUMAH Qur'an Az'Zakir
OWNER |  | : | PT. Cipta Karya Serasi
LOKASI |  | : | Cibinong, Bogor
No | URAIAN PEKERJAAN |  |  | JUMLAH
(Rp)
I | PEKERJAAN PERSIAPAN |  |  | 48550323.4161
II | PEKERJAAN TANAH + PONDASI |  |  | 338915591.3292
III | PEKERJAAN BETON |  |  | 197410130.12
IV | PEKERJAAN STRUKTUR BAJA |  |  | 207282856.6664
V | PEKERJAAN PASANGAN DINDING, LANTAI, PLESTERAN DAN ACIAN |  |  | 222523706.1677
VI | PEKERJAAN M & E |  |  | 14497640.3308
VII | PEKERJAAN SANITAIR |  |  | 47623612.6843
VIII | PEKERJAAN ATAP |  |  | 141531058.4753
IX | PEKERJAAN CARPORT |  |  | 24658510.0912
X | PEKERJAAN LAIN-LAIN |  |  | 55506570.7188
|  |  | JUMLAH I | 1298500000
|  |  | PPH 23 (2%) | 26500000
1325000000
|  |  | DIBULATKAN | 1325000000

## BOQ (Final Harga Kontrak)
RENCANA ANGGARAN BIAYA | [8 empty] | NK Incl. PPh | 1325000000
PEKERJAAN |  | : | RUMAH Qur'an Az'Zakir | [5 empty] | PPh 2% | 26500000
OWNER |  | : | PT. Cipta Karya Serasi
LOKASI |  | : | Cibinong, Bogor
OWNER |  | : | PT. Cipta Karya Serasi | [6 empty] | 1298500000
LOKASI |  | : | Cibinong, Bogor
NO | URAIAN PEKERJAAN |  |  | VOLUME |  |  | Harga Satuan Material + Upah | Jumlah Material + Upah
[7 empty] | (Rp) | (Rp)
I | LANTAI 1
I | PEKERJAAN PERSIAPAN
1 | Uitzet / Bowplank : |  |  | 128 | m1 | 0.2094% | 21238.5814 | 2718538.4162
2 | Pembersihan |  |  | 854 | m2 | 0.1397% | 2123.8581 | 1813774.8495
3 | Instalasi Air Bersih, Sumur Bor |  |  | 30 | m | 0.6951% | 300879.5489 | 9026386.4657
4 | Token Listrik |  | (Daya Listrik 2200 Watt By owner) | 1 | ls | 0.2045% | 2654822.672 | 2654822.672
5 | Mobilisasi dan Remobilisasi |  |  | 1 | ls | 0.5334% | 6925624.3619 | 6925624.3619
6 | MCK |  |  | 3 | unit | 0.03688% | 159642.9827 | 478928.9481
7 | K3 Tools |  |  | 1 | ls | 0.7111% | 9234165.8158 | 9234165.8158
8 | Keamanan |  |  | 8 | ls | 0.5689% | 923416.5816 | 7387332.6526
9 | Direksi Keet, Bedeng tenaga dan gudang material |  |  | 30 | m2 | 0.64% | 277024.9745 | 8310749.2342
[7 empty] | 0 | 48550323.4161
0
II | PEKERJAAN TANAH + PONDASI | [5 empty] | 0
1 | Urugan Field |  |  | 1 | ls | 4.978% | 64639160.7107 | 64639160.7107
2 | Pekerjaan Beton Bore Pile BP-01 - K175 |  |  | 7.6302 | m3 | 0.6334% | 1077858.0049 | 8224272.1486
3 | Pekerjaan Beton Bore Pile BP-02 - K175 |  |  | 5.2752 | m3 | 0.4379% | 1077858.0049 | 5685916.5472
4 | Pekerjaan Pembesian Bore Pile BP-01 |  |  | 877.61 | kg | 0.8067% | 11936.0827 | 10475225.5678
5 | Pekerjaan Pembesian Bore Pile BP-02 |  |  | 1411.64 | kg | 1.298% | 11936.0827 | 16849451.8299
6 | Galian Tanah : PC-01 (0,6x0,6) |  |  | 5.4 | m3 | 0.03447% | 82876.6382 | 447533.8463
7 | Galian Tanah : PC-02 (0,8x0,8) |  |  | 5.76 | m3 | 0.03676% | 82876.6382 | 477369.436
8 | Pasir Urug : PC-01 (Tebal 5 cm) |  |  | 0.9 | m3 | 0.00559% | 80646.5872 | 72581.9284
9 | Pasir Urug : PC-02 (Tebal 5 cm) |  |  | 0.96 | m3 | 0.005962% | 80646.5872 | 77420.7237
10 | Lantai Kerja : PC-01 (Tebal 5 cm) |  |  | 18 | m2 | 0.09163% | 66098.1589 | 1189766.8604
11 | Lantai Kerja : PC-02 (Tebal 5 cm) |  |  | 19.2 | m2 | 0.09773% | 66098.1589 | 1269084.6511
12 | Pekerjaan Beton Pile Cap : PC-01 |  |  | 5.4 | m3 | 0.4482% | 1077858.0049 | 5820433.2262
13 | Pekerjaan Beton Pile Cap : PC-02 |  |  | 7.488 | m3 | 0.6216% | 1077858.0049 | 8071000.7403
14 | Pekerjaan Pembesian Pile Cap : PC-01 |  |  | 588.6 | kg | 0.5411% | 11936.0827 | 7025578.2969
15 | Pekerjaan Pembesian Pile Cap : PC-02 |  |  | 900.25 | kg | 0.8275% | 11936.0827 | 10745458.4808
16 | Pekerjaan Bekisting Pile Cap : PC-01 |  |  | 39.6 | m2 | 0.4599% | 150793.9278 | 5971439.5398
17 | Pekerjaan Bekisting Pile Cap : PC-02 |  |  | 62.4 | m2 | 0.7246% | 150793.9278 | 9409541.093
18 | Galian Tie Footplate F2 |  |  | 1.836 | m3 | 0.01172% | 82876.6382 | 152161.5077
19 | Pasir Urug F2 (Tebal 5 cm) |  |  | 3.06 | m3 | 0.019% | 80646.5872 | 246778.5567
20 | Lantai Kerja F2 (Tebal 5 cm) |  |  | 3.06 | m3 | 0.01558% | 66098.1589 | 202260.3663
21 | Galian Tie Beam 2 |  |  | 18.013 | m3 | 0.115% | 82876.6382 | 1492856.8838
22 | Galian Tie Beam 3 |  |  | 9.7694 | m3 | 0.06235% | 82876.6382 | 809652.9573
23 | Galian Tie Beam 4 |  |  | 5.5739 | m3 | 0.03558% | 82876.6382 | 461944.4361
24 | Urugan Tanah Kembali |  |  | 11.16 | m3 | 0.04385% | 51018.7661 | 569369.43
25 | Pekerjaan Pembesian Wiremesh M10 |  |  | 326.21 | m2 | 1.947% | 77520.822 | 25288067.3524
26 | Pekerjaan Pengecoran beton Lantai K-175 |  |  | 39.1452 | m3 | 3.249% | 1077858.0049 | 42192967.1715
27 | Pekerjaan Beton Tie Beam 2 |  |  | 14.4104 | m3 | 1.196% | 1077858.0049 | 15532364.9931
28 | Pekerjaan Beton Tie Beam 3 |  |  | 7.9931 | m3 | 0.2419% | 392913.7555 | 3140608.7616
29 | Pekerjaan Beton Tie Beam 4 |  |  | 3.7159 | m3 | 0.3085% | 1077858.0049 | 4005234.1174
30 | Pekerjaan Pembesian Tie Beam 2 |  |  | 1525.64 | kg | 1.402% | 11936.0827 | 18210165.2616
31 | Pekerjaan Pembesian Tie Beam 3 |  |  | 641.28 | kg | 0.5895% | 11936.0827 | 7654371.1353
32 | Pekerjaan Pembesian Tie Beam 4 |  |  | 624.35 | kg | 0.5739% | 11936.0827 | 7452293.2547
33 | Pekerjaan Bekisting Tie Beam 2 |  |  | 144.104 | m2 | 1.673% | 150793.9278 | 21730008.1677
34 | Pekerjaan Bekisting Tie Beam 3 |  |  | 63.945 | m2 | 0.7426% | 150793.9278 | 9642517.7114
35 | Pekerjaan Bekisting Tie Beam 4 |  |  | 57.168 | m2 | 0.6639% | 150793.9278 | 8620587.2629
36 | Pekerjaan Pembesian Footplate F1 |  |  | 770.4 | kg | 0.7082% | 11936.0827 | 9195558.1379
37 | Pekerjaan Bekisting Footplate 'F1 |  |  | 22.68 | m2 | 0.2634% | 150793.9278 | 3420006.2819
38 | Pekerjaan Beton Footplate F1 |  |  | 2.268 | m3 | 0.1883% | 1077858.0049 | 2444581.955
| SUB TOTAL | [5 empty] | 0 | 338915591.3292
0
0
III | PEKERJAAN BETON | [5 empty] | 0
39 | Pekerjaan Pembesian Kolom K3 |  |  | 1062.5 | kg | 0.9767% | 11936.0827 | 12682087.9044
40 | Pekerjaan Bekisting Kolom K3 |  |  | 144.48 | m2 | 1.678% | 150793.9278 | 21786706.6845
41 | Pekerjaan Beton Kolom K3 |  |  | 6.552 | m3 | 0.6647% | 1317323.0099 | 8631100.3607
42 | Pekerjaan Pembesian Kolom K3a |  |  | 387.5 | kg | 0.3562% | 11936.0827 | 4625232.0592
43 | Pekerjaan Bekisting Kolom K3a |  |  | 69.6 | m2 | 0.8083% | 150793.9278 | 10495257.3729
44 | Pekerjaan Beton Kolom K3a |  |  | 3.51 | m3 | 0.3561% | 1317323.0099 | 4623803.7646
45 | Pekerjaan Pembesian Balok B1 |  |  | 595.508 | kg | 0.5474% | 11936.0827 | 7108032.7565
46 | Pekerjaan Bekisting Balok B1 |  |  | 58.52 | m2 | 0.6796% | 150793.9278 | 8824460.6532
47 | Pekerjaan Beton Balok B1 |  |  | 4.788 | m3 | 0.3974% | 1077858.0049 | 5160784.1272
48 | Pekerjaan Pembesian Balok B2 |  |  | 740.268 | kg | 0.6805% | 11936.0827 | 8835900.093
49 | Pekerjaan Bekisting Balok B2 |  |  | 33.516 | m2 | 0.3892% | 150793.9278 | 5054009.2832
50 | Pekerjaan Beton Balok B2 |  |  | 1.729 | m3 | 0.1435% | 1077858.0049 | 1863616.4904
51 | Pekerjaan Pembesian Balok B3 |  |  | 814.69 | kg | 0.7489% | 11936.0827 | 9724207.2422
52 | Pekerjaan Bekisting Balok B3 |  |  | 69.975 | m2 | 0.8126% | 150793.9278 | 10551805.0959
53 | Pekerjaan Beton Balok B3 |  |  | 4.1985 | m3 | 0.3485% | 1077858.0049 | 4525386.8334
54 | Pekerjaan Pembesian RB1 |  |  | 146.7441 | kg | 0.1349% | 11936.0827 | 1751550.069
55 | Pekerjaan Bekisting RB1 |  |  | 8.984 | m2 | 0.1043% | 150793.9278 | 1354732.6471
56 | Pekerjaan Beton RB1 |  |  | 0.3369 | m3 | 0.02797% | 1077858.0049 | 363130.3618
57 | Pekerjaan Pembesian Dak Atap |  |  | 1057.02 | kg | 0.9716% | 11936.0827 | 12616678.171
58 | Pekerjaan Bekisting Dak Atap |  |  | 183.997 | m2 | 2.137% | 150793.9278 | 27745630.3283
59 | Pekerjaan Beton Dak Atap |  |  | 22.0796 | m3 | 2.24% | 1317323.0099 | 29086017.8216
[7 empty] | 0 | 197410130.12
0
IV | PEKERJAAN STRUKTUR BAJA | [5 empty] | 0
1 | Pekerjaan kolom baja : WF-250.125 .6.9mm |  |  | 1065 | kg | 3.151% | 38414.1298 | 40911048.2304
2 | Pekerjaan balok baja : WF-250.125.6.9mm |  |  | 2340 | kg | 6.923% | 38414.1298 | 89889063.7174
3 | Pekerjaan Atap Gording WF-200.100.5,5.8mm |  |  | 742.4 | kg | 2.196% | 38414.1298 | 28518649.9589
4 | Pekerjaan Atap Gording WF-150.75.5.7mm |  |  | 1184.4 | kg | 3.504% | 38414.1298 | 45497695.3277
5 | Pekerjaan Beton Komposit Kolom WF |  |  | 1.6562 | m3 | 0.1899% | 1489146.8269 | 2466399.432
[7 empty] | 0 | 207282856.6664
V | PEKERJAAN PASANGAN DINDING, LANTAI, PLESTERAN DAN ACIAN | [5 empty] | 0 | 0
1 | Pek. Pasangan dinding 1/2 Batu (@ Bata Merah) |  |  | 497 | m2 | 3.558% | 92960.3473 | 46201292.5921
2 | Pek. Plesteran dinding |  |  | 994 | m2 | 3.882% | 50712.1918 | 50407918.6763
3 | Pek. Acian |  |  | 994 | m2 | 2.474% | 32319.5804 | 32125662.8732
3 | Openingan |  |  | 314.55 | m1 | 1.656% | 68349.4485 | 21499319.0368
4 | Pek. Pasangan Dinding Trasram |  |  | 138.73 | m2 | 1.651% | 154528.2244 | 21437700.5749
5 | Parapet |  |  | 200 | m2 | 1.418% | 92036.9307 | 18407386.1372
6 | Pekerjaan Plasteran Parapet |  |  | 200 | m2 | 0.7953% | 51635.6084 | 10327121.6818
7 | Beton Dinding Wudhu |  |  | 2 | m3 | 0.1636% | 1061929.0688 | 2123858.1376
8 | Pembesian Dinding Beton Wudhu |  |  | 162.8 | kg | 0.5441% | 43400.5793 | 7065614.3156
9 | Beton Lapangan |  |  | 8 | m3 | 0.6542% | 1061929.0688 | 8495432.5505
10 | Wire Mesh Beton Lapangan |  |  | 80 | m2 | 0.3413% | 55404.9949 | 4432399.5916
[7 empty] | 0 | 222523706.1677
0
VI | PEKERJAAN M & E | [5 empty] | 0
1 | Instalasi Lampu |  |  | 48 | ttk | 0.5359% | 144976.4033 | 6958867.3588
2 | Instalasi Stop Kontak |  |  | 15 | ttk | 0.1675% | 144976.4033 | 2174646.0496
3 | Instalasi Stop Kontak AC |  |  | 11 | ttk | 0.1228% | 144976.4033 | 1594740.4364
4 | Instalasi Saklar |  |  | 26 | bh | 0.2903% | 144976.4033 | 3769386.486
[7 empty] | 0 | 14497640.3308
VII | PEKERJAAN SANITAIR | [5 empty] | 0
1 | Pek. Pasang instalasi air kotor 4'' AW |  |  | 126 | m1 | 1.666% | 171646.521 | 21627461.6482
2 | Pek. Pasang instalasi air kotor 3'' AW |  |  | 108.5 | m1 | 1.161% | 138990.817 | 15080503.6474
3 | Pek. Pasang instalasi air bersih 1'' AW |  |  | 133.3 | m1 | 0.5858% | 57067.1447 | 7607050.3941
4 | Pek. Pasang instalasi air bersih 3/4'' AW |  |  | 66.65 | m1 | 0.2266% | 44139.3126 | 2941885.1848
5 | Pek. Pasang instalasi air bersih 1/2'' AW |  |  | 11.25 | m1 | 0.02824% | 32596.6053 | 366711.81
[7 empty] | 0 | 47623612.6843
0
0
VIII | PEKERJAAN ATAP | [5 empty] | 0
1 | Pekerjaan WF |  |  | 2195.2 | kg | 5.751% | 34018.6669 | 74677777.503
2 | Atap Bitumen |  |  | 277.45 | m2 | 3.808% | 178219.4002 | 49446972.598
3 | Bubungan Atap |  |  | 17.9 | m1 | 0.23% | 166861.3763 | 2986818.6356
4 | Talang zincalume |  |  | 35.8 | m1 | 0.331% | 120044.1556 | 4297580.7707
5 | List Plank Kalsiplank + Talang zincalume |  |  | 31 | m1 | 0.2359% | 98805.5742 | 3062972.8011
6 | Atap Onduline |  |  | 17.63 | m2 | 0.249% | 183390.5331 | 3233175.0986
7 | Rangka Atap Onduline |  |  | 17.63 | m2 | 0.2946% | 217002.8967 | 3825761.0683
[7 empty] | 0 | 141531058.4753
0
IX | PEKERJAAN CARPORT | [5 empty] | 0
| Beton carport |  |  | 130,12 | m3 | 1.046% | 104346.0737 | 13577511.1123
| Wiremesh car port |  |  | 12 | m2 | 0.8534% | 923416.5816 | 11080998.979
[7 empty] | 0 | 24658510.0912
X | PEKERJAAN LAIN-LAIN | [5 empty] | 0
1 | Konecting PAM |  |  | 5 | ls | 1.156% | 3001103.8901 | 15005519.4507
2 | CBR Test (Lapangan) |  |  | 6 | ls | 1.803% | 3901435.0572 | 23408610.3431
4 | As Built & Shopdrawing |  |  | 1 | ls | 1.067% | 13851248.7237 | 13851248.7237
5 | weekly Report |  |  | 31 | ls | 0.172% | 72026.4934 | 2232821.2943
6 | Invoice Document |  |  | 7 | ls | 0.03883% | 72026.4934 | 504185.4535
7 | Monthly Report |  |  | 7 | ls | 0.03883% | 72026.4934 | 504185.4535
55506570.7188
[7 empty] | Total Harga | 1298500000
[7 empty] | PPh 2% | 26500000
[7 empty] | Grand Total | 1325000000
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Listrik 2200 Watt

## Schedule & S-Cuve
RENCANA ANGGARAN BIAYA | [17 empty] | NK | 1325000000 | [5 empty] | Set | 350 | M2 |  | 2.16 | M2/Set | 405.0926 | set | 35000
PEKERJAAN |  | : | RUMAH Qur'an Az'Zakir | [12 empty] | Nilai Kontrak | 1325000000 |  | 21500000 |  | 1.623% | [9 empty] | 81.0185 | set | [14 empty] | Total
OWNER |  | : | PT. Cipta Karya Serasi | [12 empty] | BOQ | 26703560 | RAP | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! |  |  |  | #REF! | [11 empty] | #REF!
LOKASI |  | : | Cibinong, Bogor | [13 empty] | #REF! |  | 16018857967% |  |  |  | 24688700795% |  |  |  | 12978998600% |  |  |  | 24755137065% |  |  |  | 22569664720% | [11 empty] | 1010113591.4683
OWNER |  | : | PT. Cipta Karya Serasi | [14 empty] | DP | 20% | 265000000 |  |  | 37857142.8571 |  |  |  | 14.29%
LOKASI |  | : | Cibinong, Bogor | [12 empty] | BOQ | 1406190906.5754 | BOQ | 160188579.6657 |  |  |  | 246887007.9509 |  |  |  | 129789986.0005 |  |  |  | 247551370.6529 |  |  |  | 225696647.1983 |  |  |  | 181724458.4749 |  |  |  | 133161950.0569 |  |  |  | 1325000000
[16 empty] | BOQ | 28123818.1315 | Rencana Pembayaran | 122331436.8085 |  |  |  | 209029865.0938 |  |  |  | 91932843.1434 |  |  |  | 209694227.7957 |  |  |  | 187839504.3412 |  |  |  | 143867315.6177 |  |  |  | 95304807.1997 |  |  |  | 1060000000 | 2.3842e-07
[17 empty] | -81190906.5754 | Rencana Bobot Perbulan | 12.09% |  |  |  | 18.63% |  |  |  | 9.795% |  |  |  | 18.68% |  |  |  | 17.03% |  |  |  | 13.72% |  |  |  | 10.05% |  |  |  | 100% | 0%
[19 empty] | 3.957% | 3.957% | 2.849% | 1.326% | 2.534% | 5.769% | 5.769% | 4.561% | 4.561% | 1.745% | 1.745% | 1.745% | 4.697% | 4.697% | 4.644% | 4.644% | 5.269% | 3.196% | 4.284% | 4.284% | 2.289% | 2.289% | 4.569% | 4.569% | 3.944% | 3.944% | 2.03% | 0.1315% |  | Balance
NO | URAIAN PEKERJAAN |  |  | VOLUME |  | Haga Satuan Material | Harga Satuan Upah | Material + Upah | Jumlah Harga Material | Jumlah Harga Upah | Jumlah Material + Upah | K1 (10%) | K2 (2,5%) | K3 (2,5%) | GM (15%) | Harga Satuan Material + Upah | Total | Bobot | Juli 24 |  |  |  | Agustus 24 |  |  |  | September 24 |  |  |  | Oktober 24 |  |  |  | November 24 |  |  |  | Desember 24 |  |  |  | Januari 25
[6 empty] | (Rp) | (Rp) | (Rp) | (Rp) | (Rp) | (Rp) | [6 empty] | (%) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28
I | LANTAI 1
I | PEKERJAAN PERSIAPAN
1 | Uitzet / Bowplank : |  |  | 128 | m1 | 10000 | 10000 | 20000 | 1280000 | 1280000 | 2944000 |  |  |  | 3000 | 23000 | 2944000 | 0.2094% | 0.1047% | 0.1047% | [26 empty] | 0.2094% | 0
2 | Pembersihan |  |  | 854 | m2 | 0 | 2000 | 2000 | 0 | 1708000 | 1964200 |  |  |  | 300 | 2300 | 1964200 | 0.1397% | 0.06984% | 0.06984% | [26 empty] | 0.1397% | 0
3 | Instalasi Air Bersih, Sumur Bor |  |  | 30 | m | 183333 | 100000 | 283333 | 5499990 | 3000000 | 9774988.5 |  |  |  | 42499.95 | 325832.95 | 9774988.5 | 0.6951% | 0.3476% | 0.3476% | [26 empty] | 0.6951% | 0
4 | Token Listrik |  | (Daya Listrik 2200 Watt By owner) | 1 | ls | 1500000 | 1000000 | 2500000 | 1500000 | 1000000 | 2875000 |  |  |  | 375000 | 2875000 | 2875000 | 0.2045% | 0.1022% | 0.1022% | [26 empty] | 0.2045% | 0
5 | Mobilisasi dan Remobilisasi |  |  | 1 | ls | 0 | 7500000 | 7500000 | 0 | 7500000 | 7500000 |  |  |  |  | 7500000 | 7500000 | 0.5334% | 0.2667% | 0.2667% | [26 empty] | 0.5334% | 0
6 | MCK |  |  | 3 | unit | 111333 | 39000 | 150333 | 333999 | 117000 | 518648.85 |  |  |  | 22549.95 | 172882.95 | 518648.85 | 0.03688% | 0.01844% | 0.01844% | [26 empty] | 0.03688% | 0
7 | K3 Tools |  |  | 1 | ls | 10000000 |  |  | 10000000 |  | 10000000 | [5 empty] | 10000000 | 0.7111% | 0.3556% | 0.3556% | [26 empty] | 0.7111% | 0
8 | Keamanan |  |  | 8 | ls |  | 1000000 |  | 0 | 8000000 | 8000000 |  |  |  | 0 |  | 8000000 | 0.5689% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.02032% | 0.5689% | 0
9 | Direksi Keet, Bedeng tenaga dan gudang material |  |  | 30 | m2 | 250000 | 50000 | 300000 | 7500000 | 1500000 | 9000000 |  |  |  |  | 300000 | 9000000 | 0.64% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.02286% | 0.64% | 0
[11 empty] | 52576837.35 |  |  |  |  | Total | 52576837.35 | [29 empty] | 0% | 0
[47 empty] | 0% | 0
II | PEKERJAAN TANAH + PONDASI | [45 empty] | 0% | 0
1 | Urugan Field |  |  | 1 | ls |  | 60000000 | 60000000 | 0 | 60000000 | 60000000 | 10000000 |  |  |  | 70000000 | 70000000 | 4.978% | 1.659% | 1.659% | 1.659% | [25 empty] | 4.978% | 0
2 | Pekerjaan Beton Bore Pile BP-01 - K175 |  |  | 7.6302 | m3 | 715000 | 300000 | 1015000 | 5455593 | 2289060 | 7744653 |  |  |  | 152250 | 1167250 | 8906350.95 | 0.6334% |  |  | 0.2111% | 0.2111% | 0.2111% | [23 empty] | 0.6334% | 0
3 | Pekerjaan Beton Bore Pile BP-02 - K175 |  |  | 5.2752 | m3 | 715000 | 300000 | 1015000 | 3771768 | 1582560 | 5354328 |  |  |  | 152250 | 1167250 | 6157477.2 | 0.4379% |  |  | 0.146% | 0.146% | 0.146% | [23 empty] | 0.4379% | 0
4 | Pekerjaan Pembesian Bore Pile BP-01 |  |  | 877.61 | kg | 9240 | 2000 | 11240 | 8109116.4 | 1755220 | 9864336.4 |  |  |  | 1686 | 12926 | 11343986.86 | 0.8067% |  |  | 0.2689% | 0.2689% | 0.2689% | [23 empty] | 0.8067% | 0
5 | Pekerjaan Pembesian Bore Pile BP-02 |  |  | 1411.64 | kg | 9240 | 2000 | 11240 | 13043553.6 | 2823280 | 15866833.6 |  |  |  | 1686 | 12926 | 18246858.64 | 1.298% |  |  | 0.4325% | 0.4325% | 0.4325% | [23 empty] | 1.298% | 0
6 | Galian Tanah : PC-01 (0,6x0,6) |  |  | 5.4 | m3 | 0 | 65000 | 65000 | 0 | 351000 | 456300 | 6500 | 10000 | 5000 | 9750 | 89750 | 484650 | 0.03447% |  |  |  | 0.01723% | 0.01723% | [23 empty] | 0.03447% | 0
7 | Galian Tanah : PC-02 (0,8x0,8) |  |  | 5.76 | m3 | 0 | 65000 | 65000 | 0 | 374400 | 486720 | 6500 | 10000 | 5000 | 9750 | 89750 | 516960 | 0.03676% |  |  |  | 0.01838% | 0.01838% | [23 empty] | 0.03676% | 0
8 | Pasir Urug : PC-01 (Tebal 5 cm) |  |  | 0.9 | m3 | 15400 | 47500 | 62900 | 13860 | 42750 | 56610 | 6290 | 10000 | 5000 | 9435 | 87335 | 78601.5 | 0.00559% |  |  |  | 0.002795% | 0.002795% | [23 empty] | 0.00559% | 0
9 | Pasir Urug : PC-02 (Tebal 5 cm) |  |  | 0.96 | m3 | 15400 | 47500 | 62900 | 14784 | 45600 | 60384 | 6290 | 10000 | 5000 | 9435 | 87335 | 83841.6 | 0.005962% |  |  |  | 0.002981% | 0.002981% | [23 empty] | 0.005962% | 0
10 | Lantai Kerja : PC-01 (Tebal 5 cm) |  |  | 18 | m2 | 13200 | 36000 | 49200 | 237600 | 648000 | 885600 | 4920 | 10000 | 5000 | 7380 | 71580 | 1288440 | 0.09163% |  |  |  | 0.04581% | 0.04581% | [23 empty] | 0.09163% | 0
11 | Lantai Kerja : PC-02 (Tebal 5 cm) |  |  | 19.2 | m2 | 13200 | 36000 | 49200 | 253440 | 691200 | 944640 | 4920 | 10000 | 5000 | 7380 | 71580 | 1374336 | 0.09773% |  |  |  | 0.04887% | 0.04887% | [23 empty] | 0.09773% | 0
12 | Pekerjaan Beton Pile Cap : PC-01 |  |  | 5.4 | m3 | 715000 | 300000 | 1015000 | 3861000 | 1620000 | 5481000 |  |  |  | 152250 | 1167250 | 6303150 | 0.4482% |  |  |  |  | 0.1494% | 0.1494% | 0.1494% | [21 empty] | 0.4482% | 0
13 | Pekerjaan Beton Pile Cap : PC-02 |  |  | 7.488 | m3 | 715000 | 300000 | 1015000 | 5353920 | 2246400 | 7600320 |  |  |  | 152250 | 1167250 | 8740368 | 0.6216% |  |  |  |  | 0.2072% | 0.2072% | 0.2072% | [21 empty] | 0.6216% | 0
14 | Pekerjaan Pembesian Pile Cap : PC-01 |  |  | 588.6 | kg | 9240 | 2000 | 11240 | 5438664 | 1177200 | 6615864 |  |  |  | 1686 | 12926 | 7608243.6 | 0.5411% |  |  |  |  | 0.1804% | 0.1804% | 0.1804% | [21 empty] | 0.5411% | 0
15 | Pekerjaan Pembesian Pile Cap : PC-02 |  |  | 900.25 | kg | 9240 | 2000 | 11240 | 8318310 | 1800500 | 10118810 |  |  |  | 1686 | 12926 | 11636631.5 | 0.8275% |  |  |  |  | 0.2758% | 0.2758% | 0.2758% | [21 empty] | 0.8275% | 0
16 | Pekerjaan Bekisting Pile Cap : PC-01 |  |  | 39.6 | m2 | 102000 | 40000 | 142000 | 4039200 | 1584000 | 5623200 |  |  |  | 21300 | 163300 | 6466680 | 0.4599% |  |  |  |  | 0.1533% | 0.1533% | 0.1533% | [21 empty] | 0.4599% | 0
17 | Pekerjaan Bekisting Pile Cap : PC-02 |  |  | 62.4 | m2 | 102000 | 40000 | 142000 | 6364800 | 2496000 | 8860800 |  |  |  | 21300 | 163300 | 10189920 | 0.7246% |  |  |  |  | 0.2415% | 0.2415% | 0.2415% | [21 empty] | 0.7246% | 0
18 | Galian Tie Footplate F2 |  |  | 1.836 | m3 | 0 | 65000 | 65000 | 0 | 119340 | 119340 | 6500 | 10000 | 5000 | 9750 | 89750 | 164781 | 0.01172% | [5 empty] | 0.00293% | 0.00293% | 0.00293% | 0.00293% | [19 empty] | 0.01172% | 0
19 | Pasir Urug F2 (Tebal 5 cm) |  |  | 3.06 | m3 | 15400 | 47500 | 62900 | 47124 | 145350 | 192474 | 6290 | 10000 | 5000 | 9435 | 87335 | 267245.1 | 0.019% | [5 empty] | 0.004751% | 0.004751% | 0.004751% | 0.004751% | [19 empty] | 0.019% | 0
20 | Lantai Kerja F2 (Tebal 5 cm) |  |  | 3.06 | m3 | 13200 | 36000 | 49200 | 40392 | 110160 | 150552 | 4920 | 10000 | 5000 | 7380 | 71580 | 219034.8 | 0.01558% | [5 empty] | 0.003894% | 0.003894% | 0.003894% | 0.003894% | [19 empty] | 0.01558% | 0
21 | Galian Tie Beam 2 |  |  | 18.013 | m3 |  | 65000 | 65000 | 0 | 1170845 | 1170845 | 6500 | 10000 | 5000 | 9750 | 89750 | 1616666.75 | 0.115% | [5 empty] | 0.02874% | 0.02874% | 0.02874% | 0.02874% | [19 empty] | 0.115% | 0
22 | Galian Tie Beam 3 |  |  | 9.7694 | m3 |  | 65000 | 65000 | 0 | 635009.375 | 635009.375 | 6500 | 10000 | 5000 | 9750 | 89750 | 876801.4063 | 0.06235% | [5 empty] | 0.01559% | 0.01559% | 0.01559% | 0.01559% | [19 empty] | 0.06235% | 0
23 | Galian Tie Beam 4 |  |  | 5.5739 | m3 |  | 65000 | 65000 | 0 | 362302.2 | 362302.2 | 6500 | 10000 | 5000 | 9750 | 89750 | 500255.73 | 0.03558% | [5 empty] | 0.008894% | 0.008894% | 0.008894% | 0.008894% | [19 empty] | 0.03558% | 0
24 | Urugan Tanah Kembali |  |  | 11.16 | m3 |  | 35000 | 35000 |  | 390600 | 390600 | 3500 | 10000 | 5000 | 5250 | 55250 | 616590 | 0.04385% | [5 empty] | 0.01096% | 0.01096% | 0.01096% | 0.01096% | [19 empty] | 0.04385% | 0
25 | Pekerjaan Pembesian Wiremesh M10 |  |  | 326.21 | m2 | 70000 | 3000 | 73000 | 22834700 | 978630 | 23813330 |  |  |  | 10950 | 83950 | 27385329.5 | 1.947% | [5 empty] | 0.4869% | 0.4869% | 0.4869% | 0.4869% | [19 empty] | 1.947% | 0
26 | Pekerjaan Pengecoran beton Lantai K-175 |  |  | 39.1452 | m3 | 715000 | 300000 | 1015000 | 27988818 | 11743560 | 39732378 |  |  |  | 152250 | 1167250 | 45692234.7 | 3.249% | [5 empty] | 0.8123% | 0.8123% | 0.8123% | 0.8123% | [19 empty] | 3.249% | 0
27 | Pekerjaan Beton Tie Beam 2 |  |  | 14.4104 | m3 | 715000 | 300000 | 1015000 | 10303436 | 4323120 | 14626556 |  |  |  | 152250 | 1167250 | 16820539.4 | 1.196% | [5 empty] | 0.299% | 0.299% | 0.299% | 0.299% | [19 empty] | 1.196% | 0
28 | Pekerjaan Beton Tie Beam 3 |  |  | 7.9931 | m3 | 70000 | 300000 | 370000 | 559518.75 | 2397937.5 | 2957456.25 |  |  |  | 55500 | 425500 | 3401074.6875 | 0.2419% | [5 empty] | 0.06047% | 0.06047% | 0.06047% | 0.06047% | [19 empty] | 0.2419% | 0
29 | Pekerjaan Beton Tie Beam 4 |  |  | 3.7159 | m3 | 715000 | 300000 | 1015000 | 2656882.8 | 1114776 | 3771658.8 |  |  |  | 152250 | 1167250 | 4337407.62 | 0.3085% | [5 empty] | 0.07711% | 0.07711% | 0.07711% | 0.07711% | [19 empty] | 0.3085% | 0
30 | Pekerjaan Pembesian Tie Beam 2 |  |  | 1525.64 | kg | 9240 | 2000 | 11240 | 14096913.6 | 3051280 | 17148193.6 |  |  |  | 1686 | 12926 | 19720422.64 | 1.402% | [5 empty] | 0.3506% | 0.3506% | 0.3506% | 0.3506% | [19 empty] | 1.402% | 0
31 | Pekerjaan Pembesian Tie Beam 3 |  |  | 641.28 | kg | 9240 | 2000 | 11240 | 5925427.2 | 1282560 | 7207987.2 |  |  |  | 1686 | 12926 | 8289185.28 | 0.5895% | [5 empty] | 0.1474% | 0.1474% | 0.1474% | 0.1474% | [19 empty] | 0.5895% | 0
32 | Pekerjaan Pembesian Tie Beam 4 |  |  | 624.35 | kg | 9240 | 2000 | 11240 | 5768994 | 1248700 | 7017694 |  |  |  | 1686 | 12926 | 8070348.1 | 0.5739% | [5 empty] | 0.1435% | 0.1435% | 0.1435% | 0.1435% | [19 empty] | 0.5739% | 0
33 | Pekerjaan Bekisting Tie Beam 2 |  |  | 144.104 | m2 | 102000 | 40000 | 142000 | 14698608 | 5764160 | 20462768 |  |  |  | 21300 | 163300 | 23532183.2 | 1.673% | [5 empty] | 0.4184% | 0.4184% | 0.4184% | 0.4184% | [19 empty] | 1.673% | 0
34 | Pekerjaan Bekisting Tie Beam 3 |  |  | 63.945 | m2 | 102000 | 40000 | 142000 | 6522390 | 2557800 | 9080190 |  |  |  | 21300 | 163300 | 10442218.5 | 0.7426% | [5 empty] | 0.1856% | 0.1856% | 0.1856% | 0.1856% | [19 empty] | 0.7426% | 0
35 | Pekerjaan Bekisting Tie Beam 4 |  |  | 57.168 | m2 | 102000 | 40000 | 142000 | 5831136 | 2286720 | 8117856 |  |  |  | 21300 | 163300 | 9335534.4 | 0.6639% | [5 empty] | 0.166% | 0.166% | 0.166% | 0.166% | [19 empty] | 0.6639% | 0
36 | Pekerjaan Pembesian Footplate F1 |  |  | 770.4 | kg | 9240 | 2000 | 11240 | 7118496 | 1540800 | 8659296 |  |  |  | 1686 | 12926 | 9958190.4 | 0.7082% | [5 empty] | 0.177% | 0.177% | 0.177% | 0.177% | [19 empty] | 0.7082% | 0
37 | Pekerjaan Bekisting Footplate 'F1 |  |  | 22.68 | m2 | 102000 | 40000 | 142000 | 2313360 | 907200 | 3220560 |  |  |  | 21300 | 163300 | 3703644 | 0.2634% | [5 empty] | 0.06585% | 0.06585% | 0.06585% | 0.06585% | [19 empty] | 0.2634% | 0
38 | Pekerjaan Beton Footplate F1 |  |  | 2.268 | m3 | 715000 | 300000 | 1015000 | 1621620 | 680400 | 2302020 |  |  |  | 152250 | 1167250 | 2647323 | 0.1883% | [5 empty] | 0.04707% | 0.04707% | 0.04707% | 0.04707% | [19 empty] | 0.1883% | 0
| SUB TOTAL | [9 empty] | 50211370.575 |  |  |  |  | Total | 252368832.4138 | [29 empty] | 0% | 0
[47 empty] | 0% | 0
[47 empty] | 0% | 0
III | PEKERJAAN BETON | [45 empty] | 0% | 0
39 | Pekerjaan Pembesian Kolom K3 |  |  | 1062.5 | kg | 9240 | 2000 | 11240 | 9817500 | 2125000 | 11942500 |  |  |  | 1686 | 12926 | 13733875 | 0.9767% | [9 empty] | 0.3256% | 0.3256% | 0.3256% | [16 empty] | 0.9767% | 0
40 | Pekerjaan Bekisting Kolom K3 |  |  | 144.48 | m2 | 102000 | 40000 | 142000 | 14736960 | 5779200 | 20516160 |  |  |  | 21300 | 163300 | 23593584 | 1.678% | [9 empty] | 0.5593% | 0.5593% | 0.5593% | [16 empty] | 1.678% | 0
41 | Pekerjaan Beton Kolom K3 |  |  | 6.552 | m3 | 940500 | 300000 | 1240500 | 6162156 | 1965600 | 8127756 |  |  |  | 186075 | 1426575 | 9346919.4 | 0.6647% | [9 empty] | 0.2216% | 0.2216% | 0.2216% | [16 empty] | 0.6647% | 0
42 | Pekerjaan Pembesian Kolom K3a |  |  | 387.5 | kg | 9240 | 2000 | 11240 | 3580500 | 775000 | 4355500 |  |  |  | 1686 | 12926 | 5008825 | 0.3562% | [9 empty] | 0.1187% | 0.1187% | 0.1187% | [16 empty] | 0.3562% | 0
43 | Pekerjaan Bekisting Kolom K3a |  |  | 69.6 | m2 | 102000 | 40000 | 142000 | 7099200 | 2784000 | 9883200 |  |  |  | 21300 | 163300 | 11365680 | 0.8083% | [9 empty] | 0.2694% | 0.2694% | 0.2694% | [16 empty] | 0.8083% | 0
44 | Pekerjaan Beton Kolom K3a |  |  | 3.51 | m3 | 940500 | 300000 | 1240500 | 3301155 | 1053000 | 4354155 |  |  |  | 186075 | 1426575 | 5007278.25 | 0.3561% | [9 empty] | 0.1187% | 0.1187% | 0.1187% | [16 empty] | 0.3561% | 0
45 | Pekerjaan Pembesian Balok B1 |  |  | 595.508 | kg | 9240 | 2000 | 11240 | 5502493.92 | 1191016 | 6693509.92 |  |  |  | 1686 | 12926 | 7697536.408 | 0.5474% | [12 empty] | 0.1095% | 0.1095% | 0.1095% | 0.1095% | 0.1095% | [11 empty] | 0.5474% | 0
46 | Pekerjaan Bekisting Balok B1 |  |  | 58.52 | m2 | 102000 | 40000 | 142000 | 5969040 | 2340800 | 8309840 |  |  |  | 21300 | 163300 | 9556316 | 0.6796% | [12 empty] | 0.1359% | 0.1359% | 0.1359% | 0.1359% | 0.1359% | [11 empty] | 0.6796% | 0
47 | Pekerjaan Beton Balok B1 |  |  | 4.788 | m3 | 715000 | 300000 | 1015000 | 3423420 | 1436400 | 4859820 |  |  |  | 152250 | 1167250 | 5588793 | 0.3974% | [12 empty] | 0.07949% | 0.07949% | 0.07949% | 0.07949% | 0.07949% | [11 empty] | 0.3974% | 0
48 | Pekerjaan Pembesian Balok B2 |  |  | 740.268 | kg | 9240 | 2000 | 11240 | 6840076.32 | 1480536 | 8320612.32 |  |  |  | 1686 | 12926 | 9568704.168 | 0.6805% | [12 empty] | 0.1361% | 0.1361% | 0.1361% | 0.1361% | 0.1361% | [11 empty] | 0.6805% | 0
49 | Pekerjaan Bekisting Balok B2 |  |  | 33.516 | m2 | 102000 | 40000 | 142000 | 3418632 | 1340640 | 4759272 |  |  |  | 21300 | 163300 | 5473162.8 | 0.3892% | [12 empty] | 0.07784% | 0.07784% | 0.07784% | 0.07784% | 0.07784% | [11 empty] | 0.3892% | 0
50 | Pekerjaan Beton Balok B2 |  |  | 1.729 | m3 | 715000 | 300000 | 1015000 | 1236235 | 518700 | 1754935 |  |  |  | 152250 | 1167250 | 2018175.25 | 0.1435% | [12 empty] | 0.0287% | 0.0287% | 0.0287% | 0.0287% | 0.0287% | [11 empty] | 0.1435% | 0
51 | Pekerjaan Pembesian Balok B3 |  |  | 814.69 | kg | 9240 | 2000 | 11240 | 7527735.6 | 1629380 | 9157115.6 |  |  |  | 1686 | 12926 | 10530682.94 | 0.7489% | [12 empty] | 0.1498% | 0.1498% | 0.1498% | 0.1498% | 0.1498% | [11 empty] | 0.7489% | 0
52 | Pekerjaan Bekisting Balok B3 |  |  | 69.975 | m2 | 102000 | 40000 | 142000 | 7137450 | 2799000 | 9936450 |  |  |  | 21300 | 163300 | 11426917.5 | 0.8126% | [12 empty] | 0.1625% | 0.1625% | 0.1625% | 0.1625% | 0.1625% | [11 empty] | 0.8126% | 0
53 | Pekerjaan Beton Balok B3 |  |  | 4.1985 | m3 | 715000 | 300000 | 1015000 | 3001927.5 | 1259550 | 4261477.5 |  |  |  | 152250 | 1167250 | 4900699.125 | 0.3485% | [12 empty] | 0.0697% | 0.0697% | 0.0697% | 0.0697% | 0.0697% | [11 empty] | 0.3485% | 0
54 | Pekerjaan Pembesian RB1 |  |  | 146.7441 | kg | 9240 | 2000 | 11240 | 1355915.7555 | 293488.2588 | 1649404.0143 |  |  |  | 1686 | 12926 | 1896814.6164 | 0.1349% | [12 empty] | 0.02698% | 0.02698% | 0.02698% | 0.02698% | 0.02698% | [11 empty] | 0.1349% | 0
55 | Pekerjaan Bekisting RB1 |  |  | 8.984 | m2 | 102000 | 40000 | 142000 | 916368 | 359360 | 1275728 |  |  |  | 21300 | 163300 | 1467087.2 | 0.1043% | [12 empty] | 0.02087% | 0.02087% | 0.02087% | 0.02087% | 0.02087% | [11 empty] | 0.1043% | 0
56 | Pekerjaan Beton RB1 |  |  | 0.3369 | m3 | 715000 | 300000 | 1015000 | 240883.5 | 101070 | 341953.5 |  |  |  | 152250 | 1167250 | 393246.525 | 0.02797% | [12 empty] | 0.005593% | 0.005593% | 0.005593% | 0.005593% | 0.005593% | [11 empty] | 0.02797% | 0
57 | Pekerjaan Pembesian Dak Atap |  |  | 1057.02 | kg | 9240 | 2000 | 11240 | 9766864.8 | 2114040 | 11880904.8 |  |  |  | 1686 | 12926 | 13663040.52 | 0.9716% | [12 empty] | 0.1943% | 0.1943% | 0.1943% | 0.1943% | 0.1943% | [11 empty] | 0.9716% | 0
58 | Pekerjaan Bekisting Dak Atap |  |  | 183.997 | m2 | 102000 | 40000 | 142000 | 18767694 | 7359880 | 26127574 |  |  |  | 21300 | 163300 | 30046710.1 | 2.137% | [12 empty] | 0.4273% | 0.4273% | 0.4273% | 0.4273% | 0.4273% | [11 empty] | 2.137% | 0
59 | Pekerjaan Beton Dak Atap |  |  | 22.0796 | m3 | 940500 | 300000 | 1240500 | 20765901.42 | 6623892 | 27389793.42 |  |  |  | 186075 | 1426575 | 31498262.433 | 2.24% | [12 empty] | 0.448% | 0.448% | 0.448% | 0.448% | 0.448% | [11 empty] | 2.24% | 0
[11 empty] | 493268497.0743 |  |  |  |  | Total | 763174648.7129 | [29 empty] | 0% | 0
[47 empty] | 0% | 0
IV | PEKERJAAN STRUKTUR BAJA | [45 empty] | 0% | 0
1 | Pekerjaan kolom baja : WF-250.125 .6.9mm |  |  | 1065 | kg | 17000 | 15000 | 32000 | 18105000 | 15975000 | 34080000 | 3200 | 800 | 800 | 4800 | 41600 | 44304000 | 3.151% | [12 empty] | 0.3938% | 0.3938% | 0.3938% | 0.3938% | 0.3938% | 0.3938% | 0.3938% | 0.3938% | [8 empty] | 3.151% | 0
2 | Pekerjaan balok baja : WF-250.125.6.9mm |  |  | 2340 | kg | 17000 | 15000 | 32000 | 39780000 | 35100000 | 74880000 | 3200 | 800 | 800 | 4800 | 41600 | 97344000 | 6.923% | [12 empty] | 0.8653% | 0.8653% | 0.8653% | 0.8653% | 0.8653% | 0.8653% | 0.8653% | 0.8653% | [8 empty] | 6.923% | 0
3 | Pekerjaan Atap Gording WF-200.100.5,5.8mm |  |  | 742.4 | kg | 17000 | 15000 | 32000 | 12620800 | 11136000 | 23756800 | 3200 | 800 | 800 | 4800 | 41600 | 30883840 | 2.196% | [12 empty] | 0.2745% | 0.2745% | 0.2745% | 0.2745% | 0.2745% | 0.2745% | 0.2745% | 0.2745% | [8 empty] | 2.196% | 0
4 | Pekerjaan Atap Gording WF-150.75.5.7mm |  |  | 1184.4 | kg | 17000 | 15000 | 32000 | 20134800 | 17766000 | 37900800 | 3200 | 800 | 800 | 4800 | 41600 | 49271040 | 3.504% | [12 empty] | 0.438% | 0.438% | 0.438% | 0.438% | 0.438% | 0.438% | 0.438% | 0.438% | [8 empty] | 3.504% | 0
5 | Pekerjaan Beton Komposit Kolom WF |  |  | 1.6562 | m3 | 940500 | 300000 | 1240500 | 1557703.125 | 496875 | 2054578.125 | 124050 | 31012 | 31012 | 186075 | 1612649 | 2670949.9062 | 0.1899% | [12 empty] | 0.02374% | 0.02374% | 0.02374% | 0.02374% | 0.02374% | 0.02374% | 0.02374% | 0.02374% | [8 empty] | 0.1899% | 0
[47 empty] | 0% | 0
[11 empty] | 172672178.125 | [5 empty] | 224473829.9062 | [29 empty] | 0% | 0
[47 empty] | 0% | 0
[47 empty] | 0% | 0
V | PEKERJAAN PASANGAN DINDING, LANTAI, PLESTERAN DAN ACIAN | [45 empty] | 0% | 0
1 | Pek. Pasangan dinding 1/2 Batu (@ Bata Merah) |  |  | 497 | m2 | 47670 | 28000 | 75670 | 23691990 | 13916000 | 37607990 | 25000 |  |  |  | 100670 | 50032990 | 3.558% | [14 empty] | 0.4448% | 0.4448% | 0.4448% | 0.4448% | 0.4448% | 0.4448% | 0.4448% | 0.4448% | [6 empty] | 3.558% | 0
2 | Pek. Plesteran dinding |  |  | 994 | m2 | 14918 | 25000 | 39918 | 14828492 | 24850000 | 39678492 | 15000 |  |  |  | 54918 | 54588492 | 3.882% | [16 empty] | 0.4853% | 0.4853% | 0.4853% | 0.4853% | 0.4853% | 0.4853% | 0.4853% | 0.4853% |  |  |  |  | 3.882% | 0
3 | Pek. Acian |  |  | 994 | m2 | 5000 | 20000 | 25000 | 4970000 | 19880000 | 24850000 | 10000 |  |  |  | 35000 | 34790000 | 2.474% | [18 empty] | 0.3093% | 0.3093% | 0.3093% | 0.3093% | 0.3093% | 0.3093% | 0.3093% | 0.3093% |  |  | 2.474% | 0
3 | Openingan |  |  | 314.55 | m1 | 19018 | 35000 | 54018 | 5982111.9 | 11009250 | 16991361.9 | 20000 |  |  |  | 74018 | 23282361.9 | 1.656% | [18 empty] | 0.207% | 0.207% | 0.207% | 0.207% | 0.207% | 0.207% | 0.207% | 0.207% |  |  | 1.656% | 0
4 | Pek. Pasangan Dinding Trasram |  |  | 138.73 | m2 | 90844 | 32500 | 123344 | 12602788.12 | 4508725 | 17111513.12 | 44000 |  |  |  | 167344 | 23215633.12 | 1.651% | [18 empty] | 0.2064% | 0.2064% | 0.2064% | 0.2064% | 0.2064% | 0.2064% | 0.2064% | 0.2064% |  |  | 1.651% | 0
5 | Parapet |  |  | 200 | m2 | 47670 | 28000 | 75670 | 9534000 | 5600000 | 15134000 | 24000 |  |  |  | 99670 | 19934000 | 1.418% | [18 empty] | 0.1772% | 0.1772% | 0.1772% | 0.1772% | 0.1772% | 0.1772% | 0.1772% | 0.1772% |  |  | 1.418% | 0
6 | Pekerjaan Plasteran Parapet |  |  | 200 | m2 | 14918 | 25000 | 39918 | 2983600 | 5000000 | 7983600 | 16000 |  |  |  | 55918 | 11183600 | 0.7953% | [18 empty] | 0.09941% | 0.09941% | 0.09941% | 0.09941% | 0.09941% | 0.09941% | 0.09941% | 0.09941% |  |  | 0.7953% | 0
7 | Beton Dinding Wudhu |  |  | 2 | m3 | 700000 | 150000 | 850000 | 1400000 | 300000 | 1700000 | 300000 |  |  |  | 1150000 | 2300000 | 0.1636% | [18 empty] | 0.02045% | 0.02045% | 0.02045% | 0.02045% | 0.02045% | 0.02045% | 0.02045% | 0.02045% |  |  | 0.1636% | 0
8 | Pembesian Dinding Beton Wudhu |  |  | 162.8 | kg | 9000 | 2000 | 11000 | 1465200 | 325600 | 1790800 | 36000 |  |  |  | 47000 | 7651600 | 0.5441% | [18 empty] | 0.06802% | 0.06802% | 0.06802% | 0.06802% | 0.06802% | 0.06802% | 0.06802% | 0.06802% |  |  | 0.5441% | 0
9 | Beton Lapangan |  |  | 8 | m3 | 700000 | 150000 | 850000 | 5600000 | 1200000 | 6800000 | 300000 |  |  |  | 1150000 | 9200000 | 0.6542% | [12 empty] | 0.3271% | 0.3271% | [14 empty] | 0.6542% | 0
10 | Wire Mesh Beton Lapangan |  |  | 80 | m2 | 40000 | 4000 | 44000 | 3200000 | 320000 | 3520000 | 16000 |  |  |  | 60000 | 4800000 | 0.3413% | [12 empty] | 0.1707% | 0.1707% | [14 empty] | 0.3413% | 0
[11 empty] | 173167757.02 |  |  |  |  | Total | 240978677.02 | [29 empty] | 0 | 0
[47 empty] | 0 | 0
VI | PEKERJAAN M & E | [45 empty] | 0% | 0
1 | Instalasi Lampu |  |  | 48 | ttk | 82000 | 15000 | 97000 | 3936000 | 720000 | 4656000 | 60000 |  |  |  | 157000 | 7536000 | 0.5359% | [16 empty] | 0.06699% | 0.06699% | 0.06699% | 0.06699% | 0.06699% | 0.06699% | 0.06699% | 0.06699% |  |  |  |  | 0.5359% | 0
2 | Instalasi Stop Kontak |  |  | 15 | ttk | 82000 | 15000 | 97000 | 1230000 | 225000 | 1455000 | 60000 |  |  |  | 157000 | 2355000 | 0.1675% | [16 empty] | 0.02093% | 0.02093% | 0.02093% | 0.02093% | 0.02093% | 0.02093% | 0.02093% | 0.02093% |  |  |  |  | 0.1675% | 0
3 | Instalasi Stop Kontak AC |  |  | 11 | ttk | 82000 | 15000 | 97000 | 902000 | 165000 | 1067000 | 60000 |  |  |  | 157000 | 1727000 | 0.1228% | [16 empty] | 0.01535% | 0.01535% | 0.01535% | 0.01535% | 0.01535% | 0.01535% | 0.01535% | 0.01535% |  |  |  |  | 0.1228% | 0
4 | Instalasi Saklar |  |  | 26 | bh | 82000 | 15000 | 97000 | 2132000 | 390000 | 2522000 | 60000 |  |  |  | 157000 | 4082000 | 0.2903% | [16 empty] | 0.03629% | 0.03629% | 0.03629% | 0.03629% | 0.03629% | 0.03629% | 0.03629% | 0.03629% |  |  |  |  | 0.2903% | 0
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [35 empty] | 0 | 0
[11 empty] | 9700000 |  |  |  |  | Total | 15700000 | [29 empty] | 0 | 0
VII | PEKERJAAN SANITAIR | [45 empty] | 0% | 0
1 | Pek. Pasang instalasi air kotor 4'' AW |  |  | 126 | m1 | 125882 | 10000 | 135882 | 15861132 | 1260000 | 17121132 | 50000 |  |  |  | 185882 | 23421132 | 1.666% | [5 empty] | 0.4164% | 0.4164% | 0.4164% | 0.4164% | [19 empty] | 1.666% | 0
2 | Pek. Pasang instalasi air kotor 3'' AW |  |  | 108.5 | m1 | 95518 | 10000 | 105518 | 10363703 | 1085000 | 11448703 | 45000 |  |  |  | 150518 | 16331203 | 1.161% | [5 empty] | 0.2903% | 0.2903% | 0.2903% | 0.2903% | [19 empty] | 1.161% | 0
3 | Pek. Pasang instalasi air bersih 1'' AW |  |  | 133.3 | m1 | 29800 | 10000 | 39800 | 3972340 | 1333000 | 5305340 | 22000 |  |  |  | 61800 | 8237940 | 0.5858% | [5 empty] | 0.1465% | 0.1465% | 0.1465% | 0.1465% | [19 empty] | 0.5858% | 0
4 | Pek. Pasang instalasi air bersih 3/4'' AW |  |  | 66.65 | m1 | 19800 | 10000 | 29800 | 1319670 | 666500 | 1986170 | 18000 |  |  |  | 47800 | 3185870 | 0.2266% | [5 empty] | 0.05664% | 0.05664% | 0.05664% | 0.05664% | [19 empty] | 0.2266% | 0
5 | Pek. Pasang instalasi air bersih 1/2'' AW |  |  | 11.25 | m1 | 13300 | 10000 | 23300 | 149625 | 112500 | 262125 | 12000 |  |  |  | 35300 | 397125 | 0.02824% | [5 empty] | 0.00706% | 0.00706% | 0.00706% | 0.00706% | [19 empty] | 0.02824% | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [35 empty] | 0 | 0
[11 empty] | 36123470 |  |  |  |  | Total | 51573270 | [29 empty] | 0 | 0
[47 empty] | 0 | 0
[47 empty] | 0 | 0
VIII | PEKERJAAN ATAP | [45 empty] | 0% | 0
1 | Pekerjaan WF |  |  | 2195.2 | kg | 12645 | 12195 | 24840 | 27758304 | 26770464 | 54528768 | 12000 |  |  |  | 36840 | 80871168 | 5.751% | [22 empty] | 1.438% | 1.438% | 1.438% | 1.438% |  |  | 5.751% | 0
2 | Atap Bitumen |  |  | 277.45 | m2 | 100000 | 43000 | 143000 | 27745000 | 11930350 | 39675350 | 50000 |  |  |  | 193000 | 53547850 | 3.808% | [22 empty] | 0.952% | 0.952% | 0.952% | 0.952% |  |  | 3.808% | 0
3 | Bubungan Atap |  |  | 17.9 | m1 | 95700 | 40000 | 135700 | 1713030 | 716000 | 2429030 | 45000 |  |  |  | 180700 | 3234530 | 0.23% | [22 empty] | 0.05751% | 0.05751% | 0.05751% | 0.05751% |  |  | 0.23% | 0
4 | Talang zincalume |  |  | 35.8 | m1 | 75000 | 20000 | 95000 | 2685000 | 716000 | 3401000 | 35000 |  |  |  | 130000 | 4654000 | 0.331% | [22 empty] | 0.08274% | 0.08274% | 0.08274% | 0.08274% |  |  | 0.331% | 0
5 | List Plank Kalsiplank + Talang zincalume |  |  | 31 | m1 | 52000 | 20000 | 72000 | 1612000 | 620000 | 2232000 | 35000 |  |  |  | 107000 | 3317000 | 0.2359% | [22 empty] | 0.05897% | 0.05897% | 0.05897% | 0.05897% |  |  | 0.2359% | 0
6 | Atap Onduline |  |  | 17.63 | m2 | 116600 | 30000 | 146600 | 2055658 | 528900 | 2584558 | 52000 |  |  |  | 198600 | 3501318 | 0.249% | [22 empty] | 0.06225% | 0.06225% | 0.06225% | 0.06225% |  |  | 0.249% | 0
7 | Rangka Atap Onduline |  |  | 17.63 | m2 | 125000 | 50000 | 175000 | 2203750 | 881500 | 3085250 | 60000 |  |  |  | 235000 | 4143050 | 0.2946% | [22 empty] | 0.07366% | 0.07366% | 0.07366% | 0.07366% |  |  | 0.2946% | 0
[11 empty] | 107935956 |  |  |  |  | Total | 153268916 | [29 empty] | 0 | 0
[47 empty] | 0 | 0
IX | PEKERJAAN CARPORT | [45 empty] | 0% | 0
| Beton carport |  |  | 130,12 | m3 | 40000 | 28000 | 68000 | 5204800 | 3643360 | 8848160 | 45000 |  |  |  | 113000 | 14703560 | 1.046% | [26 empty] | 1.046% |  | 1.046% | 0
| Wiremesh car port |  |  | 12 | m2 | 800000 | 150000 | 950000 | 9600000 | 1800000 | 11400000 | 50000 |  |  |  | 1000000 | 12000000 | 0.8534% | [26 empty] | 0.8534% |  | 0.8534% | 0
[11 empty] | 20248160 | [5 empty] | 26703560 | [29 empty] | 0 | 0
X | PEKERJAAN LAIN-LAIN | [45 empty] | 0% | 0
1 | Konecting PAM |  |  | 5 | ls | 2500000 | 0 | 2500000 | 12500000 | 0 | 12500000 | 750000 |  |  |  | 3250000 | 16250000 | 1.156% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 0.04127% | 1.156% | 0
2 | CBR Test (Lapangan) |  |  | 6 | ls | 550000 | 2700000 | 3250000 | 3300000 | 16200000 | 19500000 | 975000 |  |  |  | 4225000 | 25350000 | 1.803% | 0.9014% | 0.9014% | [26 empty] | 1.803% | 0
4 | As Built & Shopdrawing |  |  | 1 | ls |  | 15000000 | 15000000 | 0 | 15000000 | 15000000 |  |  |  |  | 15000000 | 15000000 | 1.067% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 0.0381% | 1.067% | 0
5 | weekly Report |  |  | 31 | ls | 50000 | 10000 | 60000 | 1550000 | 310000 | 1860000 | 18000 |  |  |  | 78000 | 2418000 | 0.172% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.006141% | 0.172% | 0
6 | Invoice Document |  |  | 7 | ls | 50000 | 10000 | 60000 | 350000 | 70000 | 420000 | 18000 |  |  |  | 78000 | 546000 | 0.03883% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.03883% | 0
7 | Monthly Report |  |  | 7 | ls | 50000 | 10000 | 60000 | 350000 | 70000 | 420000 | 18000 |  |  |  | 78000 | 546000 | 0.03883% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.001387% | 0.03883% | 0
Bobot Rencana |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Total | 60110000 |  | 3.957% | 3.957% | 2.849% | 1.326% | 2.534% | 5.769% | 5.769% | 4.561% | 4.561% | 1.745% | 1.745% | 1.745% | 4.697% | 4.697% | 4.644% | 4.644% | 5.269% | 3.196% | 4.284% | 4.284% | 2.289% | 2.289% | 4.569% | 4.569% | 3.944% | 3.944% | 2.03% | 0.1315% | 100%
Komulatif Bobot Rencana |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0% | 3.957% | 7.914% | 10.76% | 12.09% | 14.62% | 20.39% | 26.16% | 30.72% | 35.28% | 37.03% | 38.77% | 40.52% | 45.22% | 49.91% | 54.56% | 59.2% | 64.47% | 67.67% | 71.95% | 76.23% | 78.52% | 80.81% | 85.38% | 89.95% | 93.89% | 97.84% | 99.87% | 100% | 0
[11 empty] | 49700000 | [7 empty] | 52432463.6215 | 52432463.6215 | 37753412.0178 | 17570240.4049 | 33571414.3427 | 76438922.5153 | 76438922.5153 | 60437748.5776 | 60437748.5776 | 23117412.4743 | 23117412.4743 | 23117412.4743 | 62239248.0189 | 62239248.0189 | 61536437.3076 | 61536437.3076 | 69815207.5891 | 42352770.4516 | 56764334.5788 | 56764334.5788 | 30325194.6979 | 30325194.6979 | 60537034.5395 | 60537034.5395 | 52258264.258 | 52258264.258 | 26903583.2659 | 1741838.2749
Akses Jalan
Tahap 1
Tahap 2
Tahap 3
Tahap 4
Tahap 5
Material 1
Pasir
Semen
Material 1
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Listrik 2200 Watt

## RAB
RENCANA ANGGARAN BIAYA
PEKERJAAN |  | : | RUMAH Qur'an Az'Zakir
OWNER |  | : | PT. Cipta Karya Serasi
LOKASI |  | : | Cibinong, Bogor
NO | URAIAN PEKERJAAN |  |  | VOLUME |  | Haga Satuan Material | Harga Satuan Upah | Material + Upah | Jumlah Harga Material | Jumlah Harga Upah | Jumlah Material + Upah
[6 empty] | (Rp) | (Rp) | (Rp) | (Rp) | (Rp) | (Rp)
I | LANTAI 1
I | PEKERJAAN PERSIAPAN
1 | Uitzet / Bowplank : |  |  | 128 | m1 | 10000 | 10000 | 20000 | 1280000 | 1280000 | 2944000
2 | Pembersihan |  |  | 854 | m2 | 0 | 5000 | 5000 | 0 | 4270000 | 1964200
3 | Instalasi Air Bersih, Sumur Bor |  |  | 30 | m | 183333 | 100000 | 283333 | 5499990 | 3000000 | 9774988.5
4 | Instalasi Listrik |  |  | 1 | ls | 1500000 | 1000000 | 2500000 | 1500000 | 1000000 | 2875000
5 | Mobilisasi dan Remobilisasi |  |  | 1 | ls | 0 | 7500000 | 7500000 | 0 | 7500000 | 7500000
6 | MCK |  |  | 3 | unit | 111333 | 39000 | 150333 | 333999 | 117000 | 518648.85
7 | K3 Tools |  |  | 1 | ls | 10000000 |  |  | 10000000 |  | 10000000
8 | Keamanan |  |  | 8 | ls |  | 1000000 |  | 0 | 8000000 | 8000000
9 | Direksi Keet, Bedeng tenaga dan gudang material |  |  | 30 | m2 | 250000 | 50000 | 300000 | 7500000 | 1500000 | 9000000
52576837.35
II | PEKERJAAN TANAH + PONDASI
1 | Galian Tanah : PC-01 (0,6x0,6) |  |  | 5.4 | m3 | 0 | 65000 | 65000 | 0 | 351000 | 456300
2 | Galian Tanah : PC-02 (0,8x0,8) |  |  | 5.76 | m3 | 0 | 65000 | 65000 | 0 | 374400 | 486720
3 | Pasir Urug : PC-01 (Tebal 5 cm) |  |  | 0.9 | m3 | 15400 | 37500 | 52900 | 13860 | 33750 | 47610
4 | Pasir Urug : PC-02 (Tebal 5 cm) |  |  | 0.96 | m3 | 15400 | 37500 | 52900 | 14784 | 36000 | 50784
5 | Lantai Kerja : PC-01 (Tebal 5 cm) |  |  | 18 | m2 | 13200 | 36000 | 49200 | 237600 | 648000 | 885600
6 | Lantai Kerja : PC-02 (Tebal 5 cm) |  |  | 19.2 | m2 | 13200 | 36000 | 49200 | 253440 | 691200 | 944640
7 | Galian Tie Footplate F2 |  |  | 1.836 | m3 | 0 | 65000 | 65000 | 0 | 119340 | 119340
8 | Pasir Urug F2 (Tebal 5 cm) |  |  | 3.06 | m3 | 15400 | 47500 | 62900 | 47124 | 145350 | 192474
9 | Lantai Kerja F2 (Tebal 5 cm) |  |  | 3.06 | m3 | 13200 | 36000 | 49200 | 40392 | 110160 | 150552
10 | Galian Tie Beam 2 |  |  | 18.013 | m3 |  | 65000 | 65000 | 0 | 1170845 | 1170845
11 | Galian Tie Beam 3 |  |  | 9.7694 | m3 |  | 65000 | 65000 | 0 | 635009.375 | 635009.375
12 | Galian Tie Beam 4 |  |  | 5.5739 | m3 |  | 65000 | 65000 | 0 | 362302.2 | 362302.2
13 | Urugan Tanah Kembali |  |  | 11.16 | m3 |  | 35000 | 35000 |  | 390600 | 390600
14 | Pekerjaan Beton Bore Pile BP-01 - K175 |  |  | 7.6302 | m3 | 715000 | 250000 | 965000 | 5455593 | 1907550 | 7363143
15 | Pekerjaan Beton Bore Pile BP-02 - K175 |  |  | 5.2752 | m3 | 715000 | 250000 | 965000 | 3771768 | 1318800 | 5090568
16 | Pekerjaan Pembesian Bore Pile BP-01 |  |  | 877.61 | kg | 9240 | 5000 | 14240 | 8109116.4 | 4388050 | 12497166.4
17 | Pekerjaan Pembesian Bore Pile BP-02 |  |  | 1411.64 | kg | 9240 | 5000 | 14240 | 13043553.6 | 7058200 | 20101753.6
18 | Pekerjaan Beton Pile Cap : PC-01 |  |  | 5.4 | m3 | 825000 | 250000 | 1075000 | 4455000 | 1350000 | 5805000
19 | Pekerjaan Beton Pile Cap : PC-02 |  |  | 7.488 | m3 | 825000 | 250000 | 1075000 | 6177600 | 1872000 | 8049600
20 | Pekerjaan Pembesian Pile Cap : PC-01 |  |  | 588.6 | kg | 9240 | 5000 | 14240 | 5438664 | 2943000 | 8381664
21 | Pekerjaan Pembesian Pile Cap : PC-02 |  |  | 900.25 | kg | 9240 | 5000 | 14240 | 8318310 | 4501250 | 12819560
22 | Pekerjaan Bekisting Pile Cap : PC-01 |  |  | 39.6 | m2 | 102000 | 68000 | 170000 | 4039200 | 2692800 | 6732000
23 | Pekerjaan Bekisting Pile Cap : PC-02 |  |  | 62.4 | m2 | 102000 | 68000 | 170000 | 6364800 | 4243200 | 10608000
24 | Pekerjaan Pembesian Wiremesh M10 |  |  | 326.21 | m2 | 70000 | 5000 | 75000 | 22834700 | 1631050 | 24465750
25 | Pekerjaan Pengecoran beton Lantai K-175 |  |  | 39.1452 | m3 | 825000 | 250000 | 1075000 | 32294790 | 9786300 | 42081090
26 | Pekerjaan Beton Tie Beam 2 |  |  | 14.4104 | m3 | 825000 | 250000 | 1075000 | 11888580 | 3602600 | 15491180
27 | Pekerjaan Beton Tie Beam 3 |  |  | 7.9931 | m3 | 70000 | 250000 | 320000 | 559518.75 | 1998281.25 | 2557800
28 | Pekerjaan Beton Tie Beam 4 |  |  | 3.7159 | m3 | 825000 | 250000 | 1075000 | 3065634 | 928980 | 3994614
29 | Pekerjaan Pembesian Tie Beam 2 |  |  | 1525.64 | kg | 9240 | 5000 | 14240 | 14096913.6 | 7628200 | 21725113.6
30 | Pekerjaan Pembesian Tie Beam 3 |  |  | 641.28 | kg | 9240 | 5000 | 14240 | 5925427.2 | 3206400 | 9131827.2
31 | Pekerjaan Pembesian Tie Beam 4 |  |  | 624.35 | kg | 9240 | 5000 | 14240 | 5768994 | 3121750 | 8890744
32 | Pekerjaan Bekisting Tie Beam 2 |  |  | 144.104 | m2 | 102000 | 68000 | 170000 | 14698608 | 9799072 | 24497680
33 | Pekerjaan Bekisting Tie Beam 3 |  |  | 63.945 | m2 | 102000 | 68000 | 170000 | 6522390 | 4348260 | 10870650
34 | Pekerjaan Bekisting Tie Beam 4 |  |  | 57.168 | m2 | 102000 | 68000 | 170000 | 5831136 | 3887424 | 9718560
35 | Pekerjaan Pembesian Footplate F1 |  |  | 770.4 | kg | 9240 | 5000 | 14240 | 7118496 | 3852000 | 10970496
36 | Pekerjaan Bekisting Footplate 'F1 |  |  | 22.68 | m2 | 102000 | 68000 | 170000 | 2313360 | 1542240 | 3855600
37 | Pekerjaan Beton Footplate F1 |  |  | 2.268 | m3 | 825000 | 250000 | 1075000 | 1871100 | 567000 | 2438100
| SUB TOTAL | [9 empty] | 294030436.375
III | PEKERJAAN BETON
38 | Pekerjaan Pembesian Kolom K3 |  |  | 1062.5 | kg | 9240 | 5000 | 14240 | 9817500 | 5312500 | 15130000
39 | Pekerjaan Bekisting Kolom K3 |  |  | 144.48 | m2 | 102000 | 68000 | 170000 | 14736960 | 9824640 | 24561600
40 | Pekerjaan Beton Kolom K3 |  |  | 6.552 | m3 | 825000 | 250000 | 1075000 | 5405400 | 1638000 | 7043400
41 | Pekerjaan Pembesian Kolom K3a |  |  | 387.5 | kg | 9240 | 5000 | 14240 | 3580500 | 1937500 | 5518000
42 | Pekerjaan Bekisting Kolom K3a |  |  | 69.6 | m2 | 102000 | 68000 | 170000 | 7099200 | 4732800 | 11832000
43 | Pekerjaan Beton Kolom K3a |  |  | 3.51 | m3 | 825000 | 250000 | 1075000 | 2895750 | 877500 | 3773250
44 | Pekerjaan Pembesian Balok B1 |  |  | 595.508 | kg | 9240 | 5000 | 14240 | 5502493.92 | 2977540 | 8480033.92
45 | Pekerjaan Bekisting Balok B1 |  |  | 58.52 | m2 | 102000 | 68000 | 170000 | 5969040 | 3979360 | 9948400
46 | Pekerjaan Beton Balok B1 |  |  | 4.788 | m3 | 825000 | 250000 | 1075000 | 3950100 | 1197000 | 5147100
47 | Pekerjaan Pembesian Balok B2 |  |  | 740.268 | kg | 9240 | 5000 | 14240 | 6840076.32 | 3701340 | 10541416.32
48 | Pekerjaan Bekisting Balok B2 |  |  | 33.516 | m2 | 102000 | 68000 | 170000 | 3418632 | 2279088 | 5697720
49 | Pekerjaan Beton Balok B2 |  |  | 1.729 | m3 | 825000 | 250000 | 1075000 | 1426425 | 432250 | 1858675
50 | Pekerjaan Pembesian Balok B3 |  |  | 814.69 | kg | 9240 | 5000 | 14240 | 7527735.6 | 4073450 | 11601185.6
51 | Pekerjaan Bekisting Balok B3 |  |  | 69.975 | m2 | 102000 | 68000 | 170000 | 7137450 | 4758300 | 11895750
52 | Pekerjaan Beton Balok B3 |  |  | 4.1985 | m3 | 715000 | 250000 | 965000 | 3001927.5 | 1049625 | 4051552.5
53 | Pekerjaan Pembesian RB1 |  |  | 146.7441 | kg | 9240 | 5000 | 14240 | 1355915.7555 | 733720.6469 | 2089636.4024
54 | Pekerjaan Bekisting RB1 |  |  | 8.984 | m2 | 102000 | 68000 | 170000 | 916368 | 610912 | 1527280
55 | Pekerjaan Beton RB1 |  |  | 0.3369 | m3 | 715000 | 250000 | 965000 | 240883.5 | 84225 | 325108.5
56 | Pekerjaan Pembesian Dak Atap |  |  | 1057.02 | kg | 9240 | 5000 | 14240 | 9766864.8 | 5285100 | 15051964.8
57 | Pekerjaan Bekisting Dak Atap |  |  | 183.997 | m2 | 102000 | 68000 | 170000 | 18767694 | 12511796 | 31279490
58 | Pekerjaan Beton Dak Atap |  |  | 22.0796 | m3 | 825000 | 250000 | 1075000 | 18215703 | 5519910 | 23735613
211089176.0424
IV | PEKERJAAN STRUKTUR BAJA
1 | Pekerjaan kolom baja : WF-250.125 .6.9mm |  |  | 1065 | kg | 17000 | 15000 | 32000 | 18105000 | 15975000 | 34080000
2 | Pekerjaan balok baja : WF-250.125.6.9mm |  |  | 2340 | kg | 17000 | 15000 | 32000 | 39780000 | 35100000 | 74880000
3 | Pekerjaan Atap Gording WF-200.100.5,5.8mm |  |  | 742.4 | kg | 17000 | 15000 | 32000 | 12620800 | 11136000 | 23756800
4 | Pekerjaan Atap Gording WF-150.75.5.7mm |  |  | 1184.4 | kg | 17000 | 15000 | 32000 | 20134800 | 17766000 | 37900800
5 | Pekerjaan Beton Komposit Kolom WF |  |  | 1.6562 | m3 | 825000 | 250000 | 1075000 | 1366406.25 | 414062.5 | 1780468.75
172398068.75
V | PEKERJAAN PASANGAN DINDING, LANTAI, PLESTERAN DAN ACIAN
1 | Pek. Pasangan dinding merah |  |  | 497 | m2 | 47670 | 41000 | 88670 | 23691990 | 20377000 | 44068990
2 | Pek. Plesteran dinding |  |  | 994 | m2 | 14918 | 32000 | 46918 | 14828492 | 31808000 | 46636492
3 | Pek. Acian |  |  | 994 | m2 | 5000 | 20000 | 25000 | 4970000 | 19880000 | 24850000
4 | Openingan |  |  | 314.55 | m1 | 19018 | 35000 | 54018 | 5982111.9 | 11009250 | 16991361.9
5 | Pek. Pasangan Dinding Trasram |  |  | 138.73 | m2 | 90844 | 32500 | 123344 | 12602788.12 | 4508725 | 17111513.12
6 | Parapet |  |  | 200 | m2 | 47670 | 28000 | 75670 | 9534000 | 5600000 | 15134000
7 | Pekerjaan Plasteran Parapet |  |  | 200 | m2 | 14918 | 25000 | 39918 | 2983600 | 5000000 | 7983600
8 | Beton Dinding Wudhu |  |  | 2 | m3 | 700000 | 150000 | 850000 | 1400000 | 300000 | 1700000
9 | Pembesian Dinding Beton Wudhu |  |  | 162.8 | kg | 9000 | 5000 | 14000 | 1465200 | 814000 | 2279200
10 | Beton Lapangan |  |  | 8 | m3 | 700000 | 150000 | 850000 | 5600000 | 1200000 | 6800000
11 | Wire Mesh Beton Lapangan |  |  | 80 | m2 | 40000 | 5000 | 45000 | 3200000 | 400000 | 3600000
187155157.02
VI | PEKERJAAN M & E
1 | Instalasi Lampu |  |  | 48 | ttk | 82000 | 15000 | 97000 | 3936000 | 720000 | 4656000
2 | Instalasi Stop Kontak |  |  | 15 | ttk | 82000 | 15000 | 97000 | 1230000 | 225000 | 1455000
3 | Instalasi Stop Kontak AC |  |  | 11 | ttk | 82000 | 15000 | 97000 | 902000 | 165000 | 1067000
4 | Instalasi Saklar |  |  | 26 | bh | 82000 | 15000 | 97000 | 2132000 | 390000 | 2522000
9700000
VII | PEKERJAAN SANITAIR
1 | Pek. Pasang instalasi air kotor 4'' AW |  |  | 126 | m1 | 125882 | 10000 | 135882 | 15861132 | 1260000 | 17121132
2 | Pek. Pasang instalasi air kotor 3'' AW |  |  | 108.5 | m1 | 95518 | 10000 | 105518 | 10363703 | 1085000 | 11448703
3 | Pek. Pasang instalasi air bersih 1'' AW |  |  | 133.3 | m1 | 29800 | 10000 | 39800 | 3972340 | 1333000 | 5305340
4 | Pek. Pasang instalasi air bersih 3/4'' AW |  |  | 66.65 | m1 | 14800 | 10000 | 24800 | 986420 | 666500 | 1652920
5 | Pek. Pasang instalasi air bersih 1/2'' AW |  |  | 11.25 | m1 | 14800 | 10000 | 24800 | 166500 | 112500 | 279000
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
35807095
VIII | PEKERJAAN ATAP
1 | Pekerjaan WF |  |  | 0 | kg | 12645 | 12195 | 24840 | 0 | 0 | 0
2 | Atap Bitumen |  |  | 277.45 | m2 | 100000 | 43000 | 143000 | 27745000 | 11930350 | 39675350
3 | Bubungan Atap |  |  | 17.9 | m1 | 95700 | 40000 | 135700 | 1713030 | 716000 | 2429030
4 | Talang zincalume |  |  | 35.8 | m1 | 75000 | 20000 | 95000 | 2685000 | 716000 | 3401000
5 | List Plank Kalsiplank + Talang zincalume |  |  | 31 | m1 | 52000 | 20000 | 72000 | 1612000 | 620000 | 2232000
6 | Atap Onduline |  |  | 17.63 | m2 | 116600 | 30000 | 146600 | 2055658 | 528900 | 2584558
7 | Rangka Atap Onduline |  |  | 17.63 | m2 | 125000 | 50000 | 175000 | 2203750 | 881500 | 3085250
53407188
IX | PEKERJAAN CARPORT
| Beton carport |  |  | 12.96 | m3 | 750000 | 250000 | 1000000 | 9720000 | 3240000 | 12960000
| Wiremesh car port |  |  | 12 | m2 | 65586.4198 | 67000 | 132586.4198 | 787037.037 | 804000 | 1591037.037
14551037.037
X | PEKERJAAN LAIN-LAIN
1 | Knocking PAM |  |  | 5 | ls | 2500000 | 0 | 2500000 | 12500000 | 0 | 12500000
2 | CBR Test (Lapangan) |  |  | 6 | ls | 550000 | 2700000 | 3250000 | 3300000 | 16200000 | 19500000
3 | Urugan Field |  |  | 1 | ls | 42000000 | 10000000 | 52000000 | 42000000 | 10000000 | 52000000
4 | As Built & Shopdrawing |  |  | 1 | ls |  | 15000000 | 15000000 | 0 | 15000000 | 15000000
5 | weekly Report |  |  | 31 | ls | 50000 | 10000 | 60000 | 1550000 | 310000 | 1860000
6 | Invoice Document |  |  | 7 | ls | 50000 | 10000 | 60000 | 350000 | 70000 | 420000
7 | Monthly Report |  |  | 7 | ls | 50000 | 10000 | 60000 | 350000 | 70000 | 420000
101700000
[8 empty] | Total Harga | 690643819.2525 | 441757707.9719 | 1132414995.5744
[8 empty] | Kontingensi |  | 5% | 56620749.7787
[8 empty] | PPh |  | 2% | 26500000
[8 empty] | Grand Total RAB |  |  | 1215535745.3532
[8 empty] | Nilai Kontrak |  |  | 1325000000
[8 empty] | Persentase RAB vs Nilai Kontrak |  |  | 91.74%

## VOLUME (hidden)
No | Item | Jumlah Pondasi (pcs) | Diameter (m) | Kedalaman (m) | Jumlah Tulangan Besi Utama | Diameter Besi Utama (m) | Panjang Besi Tulangan Utama (m) | Jarak Antar Besi Sengkang (m) | Diameter Besi Sengkang (m) | Jumlah Tulangan Besi Sengkang | Panjang Besi Sengkang (m) | Berat Besi Utama (btg) | Berat Besi Sengkang (btg) | Berat Besi Utama (kg) | Berat Besi Sengkang (kg) | Total Kebutuhan Besi Utama (btg) | Total Kebutuhan Besi Sengkang (btg) | Total Berat Besi Utama (kg) | Total Berat Besi Sengkang (kg) | Panjang Overlap (m) | Total Berat Besi Overlap (kg) | Total Berat Besi (kg)
1 | BP-01 | 18 | 0.3 | 6 | 6 | 0.013 | 36 | 0.15 | 0.008 | 41 | 38.6416 | 12.5 | 4.74 | 37.5 | 15.2634 | 3 | 4 | 675 | 274.7418 | 56.16 | 58.5 | 1005.9018
2 | BP-02 | 42 | 0.2 | 4 | 6 | 0.013 | 24 | 0.15 | 0.008 | 27.6667 | 26.0752 | 12.5 | 4.74 | 25 | 10.2997 | 2 | 3 | 1050 | 432.588 | 131.04 | 136.5 | 1613.628

## REKAP (hidden)
REKAPITULASI RENCANA ANGGARAN BIAYA |  |  |  | 109000000
PEKERJAAN |  | : | RUMAH Qur'an Az'Zakir
OWNER |  | : | PT. Cipta Karya Serasi | Final harga
LOKASI |  | : | Cibinong, Bogor | 1325000000
No | URAIAN PEKERJAAN |  |  | JUMLAH | Bobot
|  |  |  | (Rp) | (%)
I | PEKERJAAN PERSIAPAN |  |  | 52576837.35 | 3.739%
II | PEKERJAAN TANAH + PONDASI |  |  | 8088203.8862 | 0.5752%
III | PEKERJAAN BETON |  |  | 502717612.4129 | 35.75%
IV | PEKERJAAN STRUKTUR BAJA |  |  | 224473829.9062 | 15.96%
V | PEKERJAAN PASANGAN DINDING, LANTAI, PLESTERAN DAN ACIAN |  |  | 240978677.02 | 17.14%
VI | PEKERJAAN Instalasi M & E |  |  | 15700000 | 1.116%
VII | PEKERJAAN SANITAIR |  |  | 51573270 | 3.668%
VIII | PEKERJAAN ATAP |  |  | 153268916 | 10.9%
IX | PEKERJAAN CARPORT |  |  | 26703560 | 1.899%
X | PEKERJAAN LAIN-LAIN |  |  | 130110000 | 9.253%
|  |  | JUMLAH I | 1406190906.5754
|  |  | PPH 23 (2%) | 28123818.1315
1434314724.7069
|  |  | DIBULATKAN | 1434000000

## BOQ (hidden)
RENCANA ANGGARAN BIAYA
PEKERJAAN |  | : | RUMAH Qur'an Az'Zakir | [12 empty] | Nilai Kontrak | 1325000000
OWNER |  | : | PT. Cipta Karya Serasi | [12 empty] | BOQ | 1406190906.5754
LOKASI |  | : | Cibinong, Bogor | [13 empty] | -81190906.5754
NO | URAIAN PEKERJAAN |  |  | VOLUME |  | Haga Satuan Material | Harga Satuan Upah | Material + Upah | Jumlah Harga Material | Jumlah Harga Upah | Jumlah Material + Upah | K1 (10%) | K2 (2,5%) | K3 (2,5%) | GM (15%) | Harga Satuan Material + Upah | Total | Bobot
[6 empty] | (Rp) | (Rp) | (Rp) | (Rp) | (Rp) | (Rp) | [6 empty] | (%)
I | LANTAI 1
I | PEKERJAAN PERSIAPAN
1 | Uitzet / Bowplank : |  |  | 128 | m1 | 10000 | 10000 | 20000 | 1280000 | 1280000 | 2944000 |  |  |  | 3000 | 23000 | 2944000 | 0.2094%
2 | Pembersihan |  |  | 854 | m2 | 0 | 2000 | 2000 | 0 | 1708000 | 1964200 |  |  |  | 300 | 2300 | 1964200 | 0.1397%
3 | Instalasi Air Bersih, Sumur Bor |  |  | 30 | m | 183333 | 100000 | 283333 | 5499990 | 3000000 | 9774988.5 |  |  |  | 42499.95 | 325832.95 | 9774988.5 | 0.6951%
4 | Instalasi Listrik |  |  | 1 | ls | 1500000 | 1000000 | 2500000 | 1500000 | 1000000 | 2875000 |  |  |  | 375000 | 2875000 | 2875000 | 0.2045%
5 | Mobilisasi dan Remobilisasi |  |  | 1 | ls | 0 | 7500000 | 7500000 | 0 | 7500000 | 7500000 |  |  |  |  | 7500000 | 7500000 | 0.5334%
6 | MCK |  |  | 3 | unit | 111333 | 39000 | 150333 | 333999 | 117000 | 518648.85 |  |  |  | 22549.95 | 172882.95 | 518648.85 | 0.03688%
7 | K3 Tools |  |  | 1 | ls | 10000000 |  |  | 10000000 |  | 10000000 | [5 empty] | 10000000 | 0.7111%
8 | Keamanan |  |  | 8 | ls |  | 1000000 |  | 0 | 8000000 | 8000000 |  |  |  | 0 |  | 8000000 | 0.5689%
9 | Direksi Keet, Bedeng tenaga dan gudang material |  |  | 30 | m2 | 250000 | 50000 | 300000 | 7500000 | 1500000 | 9000000 |  |  |  |  | 300000 | 9000000 | 0.64%
[11 empty] | 52576837.35 |  |  |  |  | Total | 52576837.35
II | PEKERJAAN TANAH + PONDASI
1 | Galian Tanah : PC-01 (0,6x0,6) |  |  | 5.4 | m3 | 0 | 65000 | 65000 | 0 | 351000 | 456300 | 6500 | 10000 | 5000 | 9750 | 89750 | 484650 | 0.03447%
2 | Galian Tanah : PC-02 (0,8x0,8) |  |  | 5.76 | m3 | 0 | 65000 | 65000 | 0 | 374400 | 486720 | 6500 | 10000 | 5000 | 9750 | 89750 | 516960 | 0.03676%
4 | Pasir Urug : PC-01 (Tebal 5 cm) |  |  | 0.9 | m3 | 15400 | 47500 | 62900 | 13860 | 42750 | 56610 | 6290 | 10000 | 5000 | 9435 | 87335 | 78601.5 | 0.00559%
5 | Pasir Urug : PC-02 (Tebal 5 cm) |  |  | 0.96 | m3 | 15400 | 47500 | 62900 | 14784 | 45600 | 60384 | 6290 | 10000 | 5000 | 9435 | 87335 | 83841.6 | 0.005962%
7 | Lantai Kerja : PC-01 (Tebal 5 cm) |  |  | 18 | m2 | 13200 | 36000 | 49200 | 237600 | 648000 | 885600 | 4920 | 10000 | 5000 | 7380 | 71580 | 1288440 | 0.09163%
8 | Lantai Kerja : PC-02 (Tebal 5 cm) |  |  | 19.2 | m2 | 13200 | 36000 | 49200 | 253440 | 691200 | 944640 | 4920 | 10000 | 5000 | 7380 | 71580 | 1374336 | 0.09773%
10 | Galian Tie Footplate F2 |  |  | 1.836 | m3 | 0 | 65000 | 65000 | 0 | 119340 | 119340 | 6500 | 10000 | 5000 | 9750 | 89750 | 164781 | 0.01172%
11 | Pasir Urug F2 (Tebal 5 cm) |  |  | 3.06 | m3 | 15400 | 47500 | 62900 | 47124 | 145350 | 192474 | 6290 | 10000 | 5000 | 9435 | 87335 | 267245.1 | 0.019%
12 | Lantai Kerja F2 (Tebal 5 cm) |  |  | 3.06 | m3 | 13200 | 36000 | 49200 | 40392 | 110160 | 150552 | 4920 | 10000 | 5000 | 7380 | 71580 | 219034.8 | 0.01558%
13 | Galian Tie Beam 2 |  |  | 18.013 | m3 |  | 65000 | 65000 | 0 | 1170845 | 1170845 | 6500 | 10000 | 5000 | 9750 | 89750 | 1616666.75 | 0.115%
14 | Galian Tie Beam 3 |  |  | 9.7694 | m3 |  | 65000 | 65000 | 0 | 635009.375 | 635009.375 | 6500 | 10000 | 5000 | 9750 | 89750 | 876801.4063 | 0.06235%
15 | Galian Tie Beam 4 |  |  | 5.5739 | m3 |  | 65000 | 65000 | 0 | 362302.2 | 362302.2 | 6500 | 10000 | 5000 | 9750 | 89750 | 500255.73 | 0.03558%
16 | Urugan Tanah Kembali |  |  | 11.16 | m3 |  | 35000 | 35000 |  | 390600 | 390600 | 3500 | 10000 | 5000 | 5250 | 55250 | 616590 | 0.04385%
16 | Pekerjaan Beton Bore Pile BP-01 - K175 |  |  | 7.6302 | m3 | 715000 | 300000 | 1015000 | 5455593 | 2289060 | 7744653 |  |  |  | 152250 | 1167250 | 8906350.95 | 0.6334%
17 | Pekerjaan Beton Bore Pile BP-02 - K175 |  |  | 5.2752 | m3 | 715000 | 300000 | 1015000 | 3771768 | 1582560 | 5354328 |  |  |  | 152250 | 1167250 | 6157477.2 | 0.4379%
18 | Pekerjaan Pembesian Bore Pile BP-01 |  |  | 877.61 | kg | 9240 | 2000 | 11240 | 8109116.4 | 1755220 | 9864336.4 |  |  |  | 1686 | 12926 | 11343986.86 | 0.8067%
19 | Pekerjaan Pembesian Bore Pile BP-02 |  |  | 1411.64 | kg | 9240 | 2000 | 11240 | 13043553.6 | 2823280 | 15866833.6 |  |  |  | 1686 | 12926 | 18246858.64 | 1.298%
20 | Pekerjaan Beton Pile Cap : PC-01 |  |  | 5.4 | m3 | 715000 | 300000 | 1015000 | 3861000 | 1620000 | 5481000 |  |  |  | 152250 | 1167250 | 6303150 | 0.4482%
21 | Pekerjaan Beton Pile Cap : PC-02 |  |  | 7.488 | m3 | 715000 | 300000 | 1015000 | 5353920 | 2246400 | 7600320 |  |  |  | 152250 | 1167250 | 8740368 | 0.6216%
22 | Pekerjaan Pembesian Pile Cap : PC-01 |  |  | 588.6 | kg | 9240 | 2000 | 11240 | 5438664 | 1177200 | 6615864 |  |  |  | 1686 | 12926 | 7608243.6 | 0.5411%
23 | Pekerjaan Pembesian Pile Cap : PC-02 |  |  | 900.25 | kg | 9240 | 2000 | 11240 | 8318310 | 1800500 | 10118810 |  |  |  | 1686 | 12926 | 11636631.5 | 0.8275%
24 | Pekerjaan Bekisting Pile Cap : PC-01 |  |  | 39.6 | m2 | 102000 | 40000 | 142000 | 4039200 | 1584000 | 5623200 |  |  |  | 21300 | 163300 | 6466680 | 0.4599%
25 | Pekerjaan Bekisting Pile Cap : PC-02 |  |  | 62.4 | m2 | 102000 | 40000 | 142000 | 6364800 | 2496000 | 8860800 |  |  |  | 21300 | 163300 | 10189920 | 0.7246%
26 | Pekerjaan Pembesian Wiremesh M10 |  |  | 326.21 | m2 | 70000 | 3000 | 73000 | 22834700 | 978630 | 23813330 |  |  |  | 10950 | 83950 | 27385329.5 | 1.947%
27 | Pekerjaan Pengecoran beton Lantai K-175 |  |  | 39.1452 | m3 | 715000 | 300000 | 1015000 | 27988818 | 11743560 | 39732378 |  |  |  | 152250 | 1167250 | 45692234.7 | 3.249%
28 | Pekerjaan Beton Tie Beam 2 |  |  | 14.4104 | m3 | 715000 | 300000 | 1015000 | 10303436 | 4323120 | 14626556 |  |  |  | 152250 | 1167250 | 16820539.4 | 1.196%
29 | Pekerjaan Beton Tie Beam 3 |  |  | 7.9931 | m3 | 70000 | 300000 | 370000 | 559518.75 | 2397937.5 | 2957456.25 |  |  |  | 55500 | 425500 | 3401074.6875 | 0.2419%
30 | Pekerjaan Beton Tie Beam 4 |  |  | 3.7159 | m3 | 715000 | 300000 | 1015000 | 2656882.8 | 1114776 | 3771658.8 |  |  |  | 152250 | 1167250 | 4337407.62 | 0.3085%
31 | Pekerjaan Pembesian Tie Beam 2 |  |  | 1525.64 | kg | 9240 | 2000 | 11240 | 14096913.6 | 3051280 | 17148193.6 |  |  |  | 1686 | 12926 | 19720422.64 | 1.402%
32 | Pekerjaan Pembesian Tie Beam 3 |  |  | 641.28 | kg | 9240 | 2000 | 11240 | 5925427.2 | 1282560 | 7207987.2 |  |  |  | 1686 | 12926 | 8289185.28 | 0.5895%
33 | Pekerjaan Pembesian Tie Beam 4 |  |  | 624.35 | kg | 9240 | 2000 | 11240 | 5768994 | 1248700 | 7017694 |  |  |  | 1686 | 12926 | 8070348.1 | 0.5739%
34 | Pekerjaan Bekisting Tie Beam 2 |  |  | 144.104 | m2 | 102000 | 40000 | 142000 | 14698608 | 5764160 | 20462768 |  |  |  | 21300 | 163300 | 23532183.2 | 1.673%
35 | Pekerjaan Bekisting Tie Beam 3 |  |  | 63.945 | m2 | 102000 | 40000 | 142000 | 6522390 | 2557800 | 9080190 |  |  |  | 21300 | 163300 | 10442218.5 | 0.7426%
36 | Pekerjaan Bekisting Tie Beam 4 |  |  | 57.168 | m2 | 102000 | 40000 | 142000 | 5831136 | 2286720 | 8117856 |  |  |  | 21300 | 163300 | 9335534.4 | 0.6639%
37 | Pekerjaan Pembesian Footplate F1 |  |  | 770.4 | kg | 9240 | 2000 | 11240 | 7118496 | 1540800 | 8659296 |  |  |  | 1686 | 12926 | 9958190.4 | 0.7082%
38 | Pekerjaan Bekisting Footplate 'F1 |  |  | 22.68 | m2 | 102000 | 40000 | 142000 | 2313360 | 907200 | 3220560 |  |  |  | 21300 | 163300 | 3703644 | 0.2634%
39 | Pekerjaan Beton Footplate F1 |  |  | 2.268 | m3 | 715000 | 300000 | 1015000 | 1621620 | 680400 | 2302020 |  |  |  | 152250 | 1167250 | 2647323 | 0.1883%
| SUB TOTAL | [9 empty] | 257159465.425 |  |  |  |  | Total | 297023506.0637
III | PEKERJAAN BETON
40 | Pekerjaan Pembesian Kolom K3 |  |  | 1062.5 | kg | 9240 | 2000 | 11240 | 9817500 | 2125000 | 11942500 |  |  |  | 1686 | 12926 | 13733875 | 0.9767%
41 | Pekerjaan Bekisting Kolom K3 |  |  | 144.48 | m2 | 102000 | 40000 | 142000 | 14736960 | 5779200 | 20516160 |  |  |  | 21300 | 163300 | 23593584 | 1.678%
42 | Pekerjaan Beton Kolom K3 |  |  | 6.552 | m3 | 940500 | 300000 | 1240500 | 6162156 | 1965600 | 8127756 |  |  |  | 186075 | 1426575 | 9346919.4 | 0.6647%
43 | Pekerjaan Pembesian Kolom K3a |  |  | 387.5 | kg | 9240 | 2000 | 11240 | 3580500 | 775000 | 4355500 |  |  |  | 1686 | 12926 | 5008825 | 0.3562%
44 | Pekerjaan Bekisting Kolom K3a |  |  | 69.6 | m2 | 102000 | 40000 | 142000 | 7099200 | 2784000 | 9883200 |  |  |  | 21300 | 163300 | 11365680 | 0.8083%
45 | Pekerjaan Beton Kolom K3a |  |  | 3.51 | m3 | 940500 | 300000 | 1240500 | 3301155 | 1053000 | 4354155 |  |  |  | 186075 | 1426575 | 5007278.25 | 0.3561%
46 | Pekerjaan Pembesian Balok B1 |  |  | 595.508 | kg | 9240 | 2000 | 11240 | 5502493.92 | 1191016 | 6693509.92 |  |  |  | 1686 | 12926 | 7697536.408 | 0.5474%
47 | Pekerjaan Bekisting Balok B1 |  |  | 58.52 | m2 | 102000 | 40000 | 142000 | 5969040 | 2340800 | 8309840 |  |  |  | 21300 | 163300 | 9556316 | 0.6796%
48 | Pekerjaan Beton Balok B1 |  |  | 4.788 | m3 | 715000 | 300000 | 1015000 | 3423420 | 1436400 | 4859820 |  |  |  | 152250 | 1167250 | 5588793 | 0.3974%
49 | Pekerjaan Pembesian Balok B2 |  |  | 740.268 | kg | 9240 | 2000 | 11240 | 6840076.32 | 1480536 | 8320612.32 |  |  |  | 1686 | 12926 | 9568704.168 | 0.6805%
50 | Pekerjaan Bekisting Balok B2 |  |  | 33.516 | m2 | 102000 | 40000 | 142000 | 3418632 | 1340640 | 4759272 |  |  |  | 21300 | 163300 | 5473162.8 | 0.3892%
51 | Pekerjaan Beton Balok B2 |  |  | 1.729 | m3 | 715000 | 300000 | 1015000 | 1236235 | 518700 | 1754935 |  |  |  | 152250 | 1167250 | 2018175.25 | 0.1435%
52 | Pekerjaan Pembesian Balok B3 |  |  | 814.69 | kg | 9240 | 2000 | 11240 | 7527735.6 | 1629380 | 9157115.6 |  |  |  | 1686 | 12926 | 10530682.94 | 0.7489%
53 | Pekerjaan Bekisting Balok B3 |  |  | 69.975 | m2 | 102000 | 40000 | 142000 | 7137450 | 2799000 | 9936450 |  |  |  | 21300 | 163300 | 11426917.5 | 0.8126%
54 | Pekerjaan Beton Balok B3 |  |  | 4.1985 | m3 | 715000 | 300000 | 1015000 | 3001927.5 | 1259550 | 4261477.5 |  |  |  | 152250 | 1167250 | 4900699.125 | 0.3485%
55 | Pekerjaan Pembesian RB1 |  |  | 146.7441 | kg | 9240 | 2000 | 11240 | 1355915.7555 | 293488.2588 | 1649404.0143 |  |  |  | 1686 | 12926 | 1896814.6164 | 0.1349%
56 | Pekerjaan Bekisting RB1 |  |  | 8.984 | m2 | 102000 | 40000 | 142000 | 916368 | 359360 | 1275728 |  |  |  | 21300 | 163300 | 1467087.2 | 0.1043%
57 | Pekerjaan Beton RB1 |  |  | 0.3369 | m3 | 715000 | 300000 | 1015000 | 240883.5 | 101070 | 341953.5 |  |  |  | 152250 | 1167250 | 393246.525 | 0.02797%
58 | Pekerjaan Pembesian Dak Atap |  |  | 1057.02 | kg | 9240 | 2000 | 11240 | 9766864.8 | 2114040 | 11880904.8 |  |  |  | 1686 | 12926 | 13663040.52 | 0.9716%
59 | Pekerjaan Bekisting Dak Atap |  |  | 183.997 | m2 | 102000 | 40000 | 142000 | 18767694 | 7359880 | 26127574 |  |  |  | 21300 | 163300 | 30046710.1 | 2.137%
60 | Pekerjaan Beton Dak Atap |  |  | 22.0796 | m3 | 940500 | 300000 | 1240500 | 20765901.42 | 6623892 | 27389793.42 |  |  |  | 186075 | 1426575 | 31498262.433 | 2.24%
[11 empty] | 185897661.0743 |  |  |  |  | Total | 799741118.4767
IV | PEKERJAAN STRUKTUR BAJA
1 | Pekerjaan kolom baja : WF-250.125 .6.9mm |  |  | 1065 | kg | 17000 | 15000 | 32000 | 18105000 | 15975000 | 34080000 | 3200 | 800 | 800 | 4800 | 41600 | 44304000 | 3.151%
2 | Pekerjaan balok baja : WF-250.125.6.9mm |  |  | 2340 | kg | 17000 | 15000 | 32000 | 39780000 | 35100000 | 74880000 | 3200 | 800 | 800 | 4800 | 41600 | 97344000 | 6.923%
3 | Pekerjaan Atap Gording WF-200.100.5,5.8mm |  |  | 742.4 | kg | 17000 | 15000 | 32000 | 12620800 | 11136000 | 23756800 | 3200 | 800 | 800 | 4800 | 41600 | 30883840 | 2.196%
4 | Pekerjaan Atap Gording WF-150.75.5.7mm |  |  | 1184.4 | kg | 17000 | 15000 | 32000 | 20134800 | 17766000 | 37900800 | 3200 | 800 | 800 | 4800 | 41600 | 49271040 | 3.504%
5 | Pekerjaan Beton Komposit Kolom WF |  |  | 1.6562 | m3 | 940500 | 300000 | 1240500 | 1557703.125 | 496875 | 2054578.125 | 124050 | 31012 | 31012 | 186075 | 1612649 | 2670949.9062 | 0.1899%
[11 empty] | 172672178.125 | [5 empty] | 224473829.9062
V | PEKERJAAN PASANGAN DINDING, LANTAI, PLESTERAN DAN ACIAN
1 | Pek. Pasangan dinding hebel |  |  | 497 | m2 | 47670 | 28000 | 75670 | 23691990 | 13916000 | 37607990 | 25000 |  |  |  | 100670 | 50032990 | 3.558%
2 | Pek. Plesteran dinding |  |  | 994 | m2 | 14918 | 25000 | 39918 | 14828492 | 24850000 | 39678492 | 15000 |  |  |  | 54918 | 54588492 | 3.882%
3 | Pek. Acian |  |  | 994 | m2 | 5000 | 20000 | 25000 | 4970000 | 19880000 | 24850000 | 10000 |  |  |  | 35000 | 34790000 | 2.474%
3 | Openingan |  |  | 314.55 | m1 | 19018 | 35000 | 54018 | 5982111.9 | 11009250 | 16991361.9 | 20000 |  |  |  | 74018 | 23282361.9 | 1.656%
4 | Pek. Pasangan Dinding Trasram |  |  | 138.73 | m2 | 90844 | 32500 | 123344 | 12602788.12 | 4508725 | 17111513.12 | 44000 |  |  |  | 167344 | 23215633.12 | 1.651%
5 | Parapet |  |  | 200 | m2 | 47670 | 28000 | 75670 | 9534000 | 5600000 | 15134000 | 24000 |  |  |  | 99670 | 19934000 | 1.418%
6 | Pekerjaan Plasteran Parapet |  |  | 200 | m2 | 14918 | 25000 | 39918 | 2983600 | 5000000 | 7983600 | 16000 |  |  |  | 55918 | 11183600 | 0.7953%
7 | Beton Dinding Wudhu |  |  | 2 | m3 | 700000 | 150000 | 850000 | 1400000 | 300000 | 1700000 | 300000 |  |  |  | 1150000 | 2300000 | 0.1636%
8 | Pembesian Dinding Beton Wudhu |  |  | 162.8 | kg | 9000 | 2000 | 11000 | 1465200 | 325600 | 1790800 | 36000 |  |  |  | 47000 | 7651600 | 0.5441%
9 | Beton Lapangan |  |  | 8 | m3 | 700000 | 150000 | 850000 | 5600000 | 1200000 | 6800000 | 300000 |  |  |  | 1150000 | 9200000 | 0.6542%
10 | Wire Mesh Beton Lapangan |  |  | 80 | m2 | 40000 | 4000 | 44000 | 3200000 | 320000 | 3520000 | 16000 |  |  |  | 60000 | 4800000 | 0.3413%
[11 empty] | 173167757.02 |  |  |  |  | Total | 240978677.02
VI | PEKERJAAN M & E
1 | Instalasi Lampu |  |  | 48 | ttk | 82000 | 15000 | 97000 | 3936000 | 720000 | 4656000 | 60000 |  |  |  | 157000 | 7536000 | 0.5359%
2 | Instalasi Stop Kontak |  |  | 15 | ttk | 82000 | 15000 | 97000 | 1230000 | 225000 | 1455000 | 60000 |  |  |  | 157000 | 2355000 | 0.1675%
3 | Instalasi Stop Kontak AC |  |  | 11 | ttk | 82000 | 15000 | 97000 | 902000 | 165000 | 1067000 | 60000 |  |  |  | 157000 | 1727000 | 0.1228%
4 | Instalasi Saklar |  |  | 26 | bh | 82000 | 15000 | 97000 | 2132000 | 390000 | 2522000 | 60000 |  |  |  | 157000 | 4082000 | 0.2903%
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 9700000 |  |  |  |  | Total | 15700000
VII | PEKERJAAN SANITAIR
1 | Pek. Pasang instalasi air kotor 4'' AW |  |  | 126 | m1 | 125882 | 10000 | 135882 | 15861132 | 1260000 | 17121132 | 50000 |  |  |  | 185882 | 23421132 | 1.666%
2 | Pek. Pasang instalasi air kotor 3'' AW |  |  | 108.5 | m1 | 95518 | 10000 | 105518 | 10363703 | 1085000 | 11448703 | 45000 |  |  |  | 150518 | 16331203 | 1.161%
3 | Pek. Pasang instalasi air bersih 1'' AW |  |  | 133.3 | m1 | 29800 | 10000 | 39800 | 3972340 | 1333000 | 5305340 | 22000 |  |  |  | 61800 | 8237940 | 0.5858%
4 | Pek. Pasang instalasi air bersih 3/4'' AW |  |  | 66.65 | m1 | 19800 | 10000 | 29800 | 1319670 | 666500 | 1986170 | 18000 |  |  |  | 47800 | 3185870 | 0.2266%
5 | Pek. Pasang instalasi air bersih 1/2'' AW |  |  | 11.25 | m1 | 13300 | 10000 | 23300 | 149625 | 112500 | 262125 | 12000 |  |  |  | 35300 | 397125 | 0.02824%
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | 36123470 |  |  |  |  | Total | 51573270
VIII | PEKERJAAN ATAP
1 | Pekerjaan WF |  |  | 2195.2 | kg | 12645 | 12195 | 24840 | 27758304 | 26770464 | 54528768 | 12000 |  |  |  | 36840 | 80871168 | 5.751%
2 | Atap Bitumen |  |  | 277.45 | m2 | 100000 | 43000 | 143000 | 27745000 | 11930350 | 39675350 | 50000 |  |  |  | 193000 | 53547850 | 3.808%
3 | Bubungan Atap |  |  | 17.9 | m1 | 95700 | 40000 | 135700 | 1713030 | 716000 | 2429030 | 45000 |  |  |  | 180700 | 3234530 | 0.23%
4 | Talang zincalume |  |  | 35.8 | m1 | 75000 | 20000 | 95000 | 2685000 | 716000 | 3401000 | 35000 |  |  |  | 130000 | 4654000 | 0.331%
5 | List Plank Kalsiplank + Talang zincalume |  |  | 31 | m1 | 52000 | 20000 | 72000 | 1612000 | 620000 | 2232000 | 35000 |  |  |  | 107000 | 3317000 | 0.2359%
6 | Atap Onduline |  |  | 17.63 | m2 | 116600 | 30000 | 146600 | 2055658 | 528900 | 2584558 | 52000 |  |  |  | 198600 | 3501318 | 0.249%
7 | Rangka Atap Onduline |  |  | 17.63 | m2 | 125000 | 50000 | 175000 | 2203750 | 881500 | 3085250 | 60000 |  |  |  | 235000 | 4143050 | 0.2946%
[11 empty] | 107935956 |  |  |  |  | Total | 153268916
IX | PEKERJAAN CARPORT
| Beton carport |  |  | 130,12 | m3 | 40000 | 28000 | 68000 | 5204800 | 3643360 | 8848160 | 45000 |  |  |  | 113000 | 14703560 | 1.046%
| Wiremesh car port |  |  | 12 | m2 | 800000 | 150000 | 950000 | 9600000 | 1800000 | 11400000 | 50000 |  |  |  | 1000000 | 12000000 | 0.8534%
[11 empty] | 20248160 | [5 empty] | 26703560
X | PEKERJAAN LAIN-LAIN
1 | Knocking PAM |  |  | 5 | ls | 2500000 | 0 | 2500000 | 12500000 | 0 | 12500000 | 750000 |  |  |  | 3250000 | 16250000 | 1.156%
2 | CBR Test (Lapangan) |  |  | 6 | ls | 550000 | 2700000 | 3250000 | 3300000 | 16200000 | 19500000 | 975000 |  |  |  | 4225000 | 25350000 | 1.803%
3 | Urugan Field |  |  | 1 | ls |  | 60000000 | 60000000 | 0 | 60000000 | 60000000 | 10000000 |  |  |  | 70000000 | 70000000 | 4.978%
4 | As Built & Shopdrawing |  |  | 1 | ls |  | 15000000 | 15000000 | 0 | 15000000 | 15000000 |  |  |  |  | 15000000 | 15000000 | 1.067%
5 | weekly Report |  |  | 31 | ls | 50000 | 10000 | 60000 | 1550000 | 310000 | 1860000 | 18000 |  |  |  | 78000 | 2418000 | 0.172%
6 | Invoice Document |  |  | 7 | ls | 50000 | 10000 | 60000 | 350000 | 70000 | 420000 | 18000 |  |  |  | 78000 | 546000 | 0.03883%
7 | Monthly Report |  |  | 7 | ls | 50000 | 10000 | 60000 | 350000 | 70000 | 420000 | 18000 |  |  |  | 78000 | 546000 | 0.03883%
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Total | 130110000
|  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
109700000
1125181484.9943